## 03. CMH116 OFCI Log REV2.0
OFCI Equipment Category | AWS FBN | LLE Type | Unit Tag | Vendor | Vendor Contact | Required On Site per GC Prime Contract | Date Requested for Tickets | PAC EDD | Vendor On Site Delivery Date | ROSD Check | Actual Delivery Date | Milestone Blockers? | Notes | Push/Pull Tickets | Ticket Link | PAC v GC Contract rOSD check | GC Contractual Start Work Date | Original PAC Date
Salesforce Report 4/29/2025
Salesforce Report 8/5/2025
Salesforce Report 8/19/2025
Salesforce Report 11/3/2025
GENERATORS
Phase 1 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2025-10-20
ROMP 01 GENERATOR | CMH116ROMP01 | Generator | GEN 2.1A | ROLLS-ROYCE | Matt Schulz | 2025-11-10 | 2025-10-07 | 2025-10-31 | 2025-11-13 | -3 | 2025-11-13 |  | Crane has been rescheduled for 11/12, 11/13, and 11/14 | Pull-In Ticket Completed |  | 10 | 2025-10-20 | 2025-11-02
ROMP 01 GENERATOR | CMH116ROMP01 | Generator | GEN 2.1B | ROLLS-ROYCE | Madison Savary | 2025-11-10 | 2025-10-07 | 2025-10-31 | 2025-11-13 | -3 | 2025-11-13 |  | Crane has been rescheduled for 11/12, 11/13, and 11/14 | Pull-In Ticket Completed |  | 10 | 2025-10-20 | 2025-11-02
ROMP 01 GENERATOR | CMH116ROMP01 | Generator | GEN 1.1C | ROLLS-ROYCE | Matt Schulz | 2025-11-10 | 2025-10-07 | 2025-10-31 | 2025-11-13 | -3 | 2025-11-13 |  | Crane has been rescheduled for 11/12, 11/13, and 11/14 | Pull-In Ticket Completed |  | 10 | 2025-10-20 | 2025-11-02
ROMP 01 GENERATOR | CMH116ROMP01 | Generator | GEN 2.1C | ROLLS-ROYCE | Madison Savary | 2025-11-10 | 2025-10-07 | 2025-10-31 | 2025-11-12 | -3 | 2025-11-13 |  | Crane has been rescheduled for 11/12, 11/13, and 11/14 | Pull-In Ticket Completed |  | 10 | 2025-10-20 | 2025-11-02
ROMP 01 GENERATOR | CMH116ROMP01 | Generator | GEN House | ROLLS-ROYCE | Matt Schulz | 2025-11-10 | 2025-10-07 |  | 2025-11-12 | -3 | 2025-11-13 |  | Crane has been rescheduled for 11/12, 11/13, and 11/14 | Pull-In Ticket Completed |  |  | 2025-10-20 | 2025-11-02
ROMP01 SCR | CMH116ROMP01 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2025-11-10 |  |  | 2025-12-01 | -21 | 2025-12-01 |  | Delivering 11/6 and 11/7 |  |  |  | 2025-10-20
ROMP 01 LOOSE PARTS | CMH116ROMP01 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2025-11-10 |  |  | 2025-10-23 | -2 | 2025-11-12 | [5 empty] | 2025-10-20
Phase 2 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-01-05
ROMP 02 GENERATOR | CMH116ROMP02 | Generator | GEN 1.1A | ROLLS-ROYCE | Matt Schulz | 2026-01-26 | 2025-10-08 | 2025-11-14 | 2025-11-13 | 74 | 2025-11-13 |  | Crane has been rescheduled for 11/12, 11/13, and 11/14 | Pull-In Ticket Completed |  | 73 | 2026-01-05 | 2026-01-19
ROMP 02 GENERATOR | CMH116ROMP02 | Generator | GEN 1.1B | ROLLS-ROYCE | Madison Savary | 2026-01-26 | 2025-10-08 | 2025-11-14 | 2025-11-13 | 74 | 2025-11-13 |  | Crane has been rescheduled for 11/12, 11/13, and 11/14 | Pull-In Ticket Completed |  | 73 | 2026-01-05 | 2026-01-19
ROMP02 SCR | CMH116ROMP02 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-01-26 |  |  | 2025-12-03 | 54 | 2025-12-03 | [5 empty] | 2026-01-05
ROMP 02 LOOSE PARTS | CMH116ROMP02 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-01-26 |  |  | 2025-11-06 | 81 | 2025-11-06 | [5 empty] | 2026-01-05
Phase 3 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-01-26
ROMP 03 GENERATOR | CMH116ROMP03 | Generator | GEN 2.2A | ROLLS-ROYCE | Matt Schulz | 2026-02-16 | 2025-11-11 | 2025-11-20 | 2025-11-21 | 87 | 2025-11-21 |  |  | Pull-In Ticket Completed |  | 88 | 2026-01-26 | 2026-02-09
ROMP 03 GENERATOR | CMH116ROMP03 | Generator | GEN 2.2B | ROLLS-ROYCE | Madison Savary | 2026-02-16 | 2025-11-11 | 2025-11-20 | 2025-11-21 | 87 | 2025-11-21 |  |  | Pull-In Ticket Completed |  | 88 | 2026-01-26 | 2026-02-09
ROMP03 SCR | CMH116ROMP03 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-02-16 |  |  | 2025-12-09 | 69 | 2025-12-09 |  | In storage at Atlas Crane |  |  |  | 2026-01-26
ROMP 03 LOOSE PARTS | CMH116ROMP03 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-02-16 |  |  | 2025-11-13 | 90 | 2025-11-18 | [5 empty] | 2026-01-26
Phase 4 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-02-16
ROMP 04 GENERATOR | CMH116ROMP04 | Generator | GEN 1.2A | ROLLS-ROYCE | Matt Schulz | 2026-03-09 | 2025-12-05 | 2025-11-27 | 2025-12-05 | 94 | 2025-12-05 |  |  | Pull-In Ticket Completed |  | 102 | 2026-02-16 | 2026-03-02
ROMP 04 GENERATOR | CMH116ROMP04 | Generator | GEN 1.2B | ROLLS-ROYCE | Madison Savary | 2026-03-09 | 2025-12-05 | 2025-11-27 | 2025-12-05 | 94 | 2025-12-05 |  |  | Push-Out Ticket Completed |  | 102 | 2026-02-16 | 2026-03-02
ROMP04 SCR | CMH116ROMP04 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-03-09 |  |  | 2025-12-09 | 90 | 2025-12-09 |  | In storage at Atlas Crane |  |  |  | 2026-02-16
ROMP 04 LOOSE PARTS | CMH116ROMP04 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-03-09 |  |  | 2025-11-20 | 104 | 2025-11-25 | [5 empty] | 2026-02-16
Phase 5 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-03-09
ROMP 05 GENERATOR | CMH116ROMP05 | Generator | GEN 2.3A | ROLLS-ROYCE | Matt Schulz | 2026-03-30 | 2025-12-19 | 2025-12-19 | 2025-12-18 | 102 |  |  |  | Push-Out Ticket Completed |  | 101 | 2026-03-09 | 2026-03-23
ROMP 05 GENERATOR | CMH116ROMP05 | Generator | GEN 2.3B | ROLLS-ROYCE | Madison Savary | 2026-03-30 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 101 |  |  |  | Push-Out Ticket Completed |  | 101 | 2026-03-09 | 2026-03-23
ROMP05 SCR | CMH116ROMP05 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-03-30 |  |  | 2025-12-22 | 98 | [6 empty] | 2026-03-09
ROMP 05 LOOSE PARTS | CMH116ROMP05 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-03-30 |  | 2025-12-03 | 2025-12-16 | 104 | 2025-12-16 |  |  |  |  | 117 | 2026-03-09
Phase 6 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-03-30
ROMP 06 GENERATOR | CMH116ROMP06 | Generator | GEN 1.3A | ROLLS-ROYCE | Matt Schulz | 2026-04-20 | 2025-12-10 | 2025-12-18 | 2025-12-18 | 123 |  |  |  | Pull-In Ticket Completed |  | 123 | 2026-03-30 | 2026-04-13
ROMP 06 GENERATOR | CMH116ROMP06 | Generator | GEN 1.3B | ROLLS-ROYCE | Madison Savary | 2026-04-20 | 2025-12-10 | 2025-12-18 | 2025-12-19 | 122 |  |  |  | Pull-In Ticket Completed |  | 123 | 2026-03-30 | 2026-04-13
ROMP06 SCR | CMH116ROMP06 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-04-20 |  |  | 2025-12-22 | 119 | [6 empty] | 2026-03-30
ROMP 06 LOOSE PARTS | CMH116ROMP06 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-04-20 |  | 2025-12-10 | 2025-12-16 | 125 | 2025-12-16 |  |  |  |  | 131 | 2026-03-30
Phase 7 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-04-20
ROMP 07 GENERATOR | CMH116ROMP07 | Generator | GEN 2.4A | ROLLS-ROYCE | Matt Schulz | 2026-05-11 | 2026-02-03 | 2026-01-16 | 2026-01-15 | 116 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-04-20 | 2026-05-04
ROMP 07 GENERATOR | CMH116ROMP07 | Generator | GEN 2.4B | ROLLS-ROYCE | Madison Savary | 2026-05-11 | 2026-02-03 | 2026-01-16 | 2026-01-16 | 115 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-04-20 | 2026-05-04
ROMP07 SCR | CMH116ROMP07 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-05-11 |  |  | 2026-02-11 | 89 | [6 empty] | 2026-04-20
ROMP 07 LOOSE PARTS | CMH116ROMP07 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-05-11 |  | 2026-01-07 | 2026-01-08 | 123 | [5 empty] | 124 | 2026-04-20
Phase 8 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-05-11
ROMP 08 GENERATOR | CMH116ROMP08 | Generator | GEN 1.4A | ROLLS-ROYCE | Matt Schulz | 2026-06-01 | 2026-02-04 | 2026-02-06 | 2026-02-06 | 115 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-05-11 | 2026-05-25
ROMP 08 GENERATOR | CMH116ROMP08 | Generator | GEN 1.4B | ROLLS-ROYCE | Madison Savary | 2026-06-01 | 2026-02-04 | 2026-02-06 | 2026-02-06 | 115 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-05-11 | 2026-05-25
ROMP08 SCR | CMH116ROMP08 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-06-01 |  |  | 2026-02-11 | 110 | [6 empty] | 2026-05-11
ROMP 08 LOOSE PARTS | CMH116ROMP08 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-06-01 |  | 2026-01-28 | 2026-01-29 | 123 | [5 empty] | 124 | 2026-05-11
Phase 9 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-06-01
ROMP 09 GENERATOR | CMH116ROMP09 | Generator | GEN 2.5A | ROLLS-ROYCE | Matt Schulz | 2026-06-22 | 2026-03-17 | 2026-02-27 | 2026-02-27 | 115 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-06-01 | 2026-06-15
ROMP 09 GENERATOR | CMH116ROMP09 | Generator | GEN 2.5B | ROLLS-ROYCE | Madison Savary | 2026-06-22 | 2026-03-17 | 2026-02-27 | 2026-02-27 | 115 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-06-01 | 2026-06-15
ROMP09 SCR | CMH116ROMP09 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-06-22 |  |  | 2026-03-05 | 109 | [6 empty] | 2026-06-01
ROMP 09 LOOSE PARTS | CMH116ROMP09 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-06-22 |  | 2026-02-18 | 2026-02-19 | 123 | [5 empty] | 124 | 2026-06-01
Phase 10 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-06-22
ROMP 10 GENERATOR | CMH116ROMP10 | Generator | GEN 1.5A | ROLLS-ROYCE | Matt Schulz | 2026-07-13 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 115 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-06-22 | 2026-07-06
ROMP 10 GENERATOR | CMH116ROMP10 | Generator | GEN 1.5B | ROLLS-ROYCE | Madison Savary | 2026-07-13 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 115 |  |  |  | Pull-In Ticket Completed |  | 115 | 2026-06-22 | 2026-07-06
ROMP10 SCR | CMH116ROMP10 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-07-13 |  |  | 2026-03-26 | 109 | [6 empty] | 2026-06-22
ROMP 10 LOOSE PARTS | CMH116ROMP10 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-07-13 |  | 2026-03-11 | 2026-03-12 | 123 | [5 empty] | 124 | 2026-06-22
Phase 11 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-07-13
ROMP 11 GENERATOR | CMH116ROMP11 | Generator | GEN 2.6A | ROLLS-ROYCE | Matt Schulz | 2026-08-03 | 2026-04-28 | 2026-04-03 | 2026-04-03 | 122 |  |  |  | Pull-In Ticket Completed |  | 122 | 2026-07-13 | 2026-07-27
ROMP 11 GENERATOR | CMH116ROMP11 | Generator | GEN 2.6B | ROLLS-ROYCE | Madison Savary | 2026-08-03 | 2026-04-28 | 2026-04-03 | 2026-04-03 | 122 |  |  |  | Pull-In Ticket Completed |  | 122 | 2026-07-13 | 2026-07-27
ROMP11 SCR | CMH116ROMP11 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-08-03 |  |  | 2026-04-09 | 116 | [6 empty] | 2026-07-13
ROMP 11 LOOSE PARTS | CMH116ROMP11 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-08-03 |  | 2026-03-25 | 2026-03-26 | 130 | [5 empty] | 131 | 2026-07-13
Phase 12 |  | Generator |  | ROLLS-ROYCE | [12 empty] | 2026-08-03
ROMP 12 GENERATOR | CMH116ROMP12 | Generator | GEN 1.6A | ROLLS-ROYCE | Matt Schulz | 2026-08-24 | 2026-04-29 | 2026-04-10 | 2026-04-10 | 136 |  |  |  | Pull-In Ticket Completed |  | 136 | 2026-08-03 | 2026-08-17
ROMP 12 GENERATOR | CMH116ROMP12 | Generator | GEN 1.6B | ROLLS-ROYCE | Madison Savary | 2026-08-24 | 2026-04-29 | 2026-04-10 | 2026-04-10 | 136 |  |  |  | Pull-In Ticket Completed |  | 136 | 2026-08-03 | 2026-08-17
ROMP12 SCR | CMH116ROMP12 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-08-24 |  |  | 2026-04-16 | 130 | [6 empty] | 2026-08-03
ROMP 12 LOOSE PARTS | CMH116ROMP12 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-08-24 |  | 2026-04-01 | 2026-04-02 | 144 | [5 empty] | 145 | 2026-08-03
2026-08-03
LV SWITCHGEAR | [12 empty] | Going to PreFab
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | 2.1 | EATON | Marcella Bocciardi | 2025-11-03 | 2025-08-25 | 2025-11-02 | 2025-09-15 | -18 | 2025-11-21 |  | currently missing 3 parts | Pull-In Ticket Rejected |  | 1 | 2025-10-20
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2025-08-25 | 2025-11-02 | 2025-09-15 |  | 2025-10-01
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2025-08-25 | 2025-11-02 | 2025-09-15 |  | 2025-10-01
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2025-08-25 | 2025-11-02 | 2025-09-15 |  | 2025-10-06
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2025-08-25 | 2025-11-02 | 2025-09-15 |  | 2025-10-27
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2025-08-25 | 2025-11-02 | 2025-09-15 |  | 2025-11-21 |  | Waiting for 2 HUPP Panels
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | Switchboards | EATON | Marcella Bocciardi |  | 2025-08-25 | 2025-11-02 | 2025-09-15 |  | 2025-12-15 |  | HSSB Switchboard ship 12/12/25
ROMP 01 LV SWITCHGEAR | CMH116ROMP01 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2025-08-25 | 2025-11-02 | 2025-09-15 |  | 2025-09-08
ROMP 02 LV SWITCHGEAR | CMH116ROMP02 | LV Switchgear | 1.1 | EATON | Marcella Bocciardi | 2026-01-19 | 2025-10-20 | 2025-12-31 | 2025-10-27 | 59 | 2025-11-21 |  |  | Pull-In Ticket Completed |  | 19 | 2026-01-05
ROMP 02 LV SWITCHGEAR | CMH116ROMP02 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2025-10-20 | 2025-12-31 | 2025-10-27 |  | 2025-10-06
ROMP 02 LV SWITCHGEAR | CMH116ROMP02 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2025-10-20 | 2025-12-31 | 2025-10-27 |  | 2025-10-06
ROMP 02 LV SWITCHGEAR | CMH116ROMP02 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2025-10-20 | 2025-12-31 | 2025-10-27 |  | 2025-10-21
ROMP 02 LV SWITCHGEAR | CMH116ROMP02 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2025-10-20 | 2025-12-31 | 2025-10-27 |  | 2025-11-21
ROMP 02 LV SWITCHGEAR | CMH116ROMP02 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2025-10-20 | 2025-12-31 | 2025-10-27 |  | 2025-11-21
ROMP 02 LV SWITCHGEAR | CMH116ROMP02 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2025-10-20 | 2025-12-31 | 2025-10-27 |  | 2025-10-09
ROMP 03 LV SWITCHGEAR | CMH116ROMP03 | LV Switchgear | 2.2 | EATON | Marcella Bocciardi | 2026-02-09 | 2025-11-10 | 2026-01-07 | 2025-10-27 | 105 |  |  |  | Pull-In Ticket Completed |  | 33 | 2026-01-26
ROMP 03 LV SWITCHGEAR | CMH116ROMP03 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2025-11-10 | 2026-01-07 | 2025-10-27 |  | 2025-10-09
ROMP 03 LV SWITCHGEAR | CMH116ROMP03 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2025-11-10 | 2026-01-07 | 2025-10-27 |  | 2025-10-09
ROMP 03 LV SWITCHGEAR | CMH116ROMP03 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2025-11-10 | 2026-01-07 | 2025-10-27 |  |  |  | Missing 6 ATS ship date 12-29-25
ROMP 03 LV SWITCHGEAR | CMH116ROMP03 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2025-11-10 | 2026-01-07 | 2025-12-23 |  | 2025-10-09
ROMP 03 LV SWITCHGEAR | CMH116ROMP03 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2025-11-10 | 2026-01-07 | 2025-12-23 |  |  |  | Waiting for MSDB ship date 12-24-25
ROMP 04 LV SWITCHGEAR | CMH116ROMP04 | LV Switchgear | 1.2 | EATON | Marcella Bocciardi | 2026-03-02 | 2025-12-01 | 2026-01-14 | 2026-01-04 | 57 |  |  |  | Pull-In Ticket Completed |  | 47 | 2026-02-16
ROMP 04 LV SWITCHGEAR | CMH116ROMP04 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2025-12-01 |  |  |  | 2025-10-07
ROMP 04 LV SWITCHGEAR | CMH116ROMP04 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2025-12-01 |  |  |  | 2025-10-07
ROMP 04 LV SWITCHGEAR | CMH116ROMP04 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2025-12-01
ROMP 04 LV SWITCHGEAR | CMH116ROMP04 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2025-12-01
ROMP 04 LV SWITCHGEAR | CMH116ROMP04 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2025-12-01
ROMP 05 LV SWITCHGEAR | CMH116ROMP05 | LV Switchgear | 2.3 | EATON | Marcella Bocciardi | 2026-03-23 | 2025-12-22 | 2026-01-21 | 2026-01-25 | 57 |  |  |  | Pull-In Ticket Completed |  | 61 | 2026-03-09
ROMP 05 LV SWITCHGEAR | CMH116ROMP05 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2025-12-22 | 2025-12-22
ROMP 05 LV SWITCHGEAR | CMH116ROMP05 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2025-12-22 | 2025-12-22
ROMP 05 LV SWITCHGEAR | CMH116ROMP05 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2025-12-22 | 2025-12-22
ROMP 05 LV SWITCHGEAR | CMH116ROMP05 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2025-12-22 | 2025-12-22
ROMP 05 LV SWITCHGEAR | CMH116ROMP05 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2025-12-22 | 2025-12-22
ROMP 05 LV SWITCHGEAR | CMH116ROMP05 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2025-12-22 | 2025-12-22
ROMP 06 LV SWITCHGEAR | CMH116ROMP06 | LV Switchgear | 1.3 | EATON | Marcella Bocciardi | 2026-04-13 | 2026-01-13 | 2026-01-28 | 2026-02-08 | 64 |  |  |  | Pull-In Ticket Completed |  | 75 | 2026-03-30
ROMP 06 LV SWITCHGEAR | CMH116ROMP06 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2026-01-13 | 2026-01-13
ROMP 06 LV SWITCHGEAR | CMH116ROMP06 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2026-01-13 | 2026-01-13
ROMP 06 LV SWITCHGEAR | CMH116ROMP06 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2026-01-13 | 2026-01-13
ROMP 06 LV SWITCHGEAR | CMH116ROMP06 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2026-01-13 | 2026-01-13
ROMP 06 LV SWITCHGEAR | CMH116ROMP06 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2026-01-13 | 2026-01-13
ROMP 06 LV SWITCHGEAR | CMH116ROMP06 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2026-01-13 | 2026-01-13
ROMP 07 LV SWITCHGEAR | CMH116ROMP07 | LV Switchgear | 2.4 | EATON | Marcella Bocciardi | 2026-05-04 | 2026-02-22 | 2026-02-22 | 2026-02-22 | 71 |  |  |  | Pull-In Ticket Completed |  | 71 | 2026-04-20
ROMP 07 LV SWITCHGEAR | CMH116ROMP07 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2026-02-22 | 2026-02-22
ROMP 07 LV SWITCHGEAR | CMH116ROMP07 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2026-02-22 | 2026-02-22
ROMP 07 LV SWITCHGEAR | CMH116ROMP07 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2026-02-22 | 2026-02-22
ROMP 07 LV SWITCHGEAR | CMH116ROMP07 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2026-02-22 | 2026-02-22
ROMP 07 LV SWITCHGEAR | CMH116ROMP07 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2026-02-22 | 2026-02-22
ROMP 07 LV SWITCHGEAR | CMH116ROMP07 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2026-02-22 | 2026-02-22
ROMP 08 LV SWITCHGEAR | CMH116ROMP08 | LV Switchgear | 1.4 | EATON | Marcella Bocciardi | 2026-05-25 | 2026-02-23 | 2026-02-23 | 2026-03-08 | 78 |  |  |  | Pull-In Ticket Completed |  | 91 | 2026-05-11
ROMP 08 LV SWITCHGEAR | CMH116ROMP08 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2026-02-23 | 2026-02-23
ROMP 08 LV SWITCHGEAR | CMH116ROMP08 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2026-02-23 | 2026-02-23
ROMP 08 LV SWITCHGEAR | CMH116ROMP08 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2026-02-23 | 2026-02-23
ROMP 08 LV SWITCHGEAR | CMH116ROMP08 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2026-02-23 | 2026-02-23
ROMP 08 LV SWITCHGEAR | CMH116ROMP08 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2026-02-23 | 2026-02-23
ROMP 08 LV SWITCHGEAR | CMH116ROMP08 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2026-02-23 | 2026-02-23
ROMP 09 LV SWITCHGEAR | CMH116ROMP09 | LV Switchgear | 2.5 | EATON | Marcella Bocciardi | 2026-06-15 | 2026-03-16 | 2026-03-16 | 2026-03-22 | 85 |  |  | Vendor confirmed pull-in request | Pull-In Ticket Completed |  | 91 | 2026-06-01
ROMP 09 LV SWITCHGEAR | CMH116ROMP09 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2026-03-16 | 2026-03-16
ROMP 09 LV SWITCHGEAR | CMH116ROMP09 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2026-03-16 | 2026-03-16
ROMP 09 LV SWITCHGEAR | CMH116ROMP09 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2026-03-16 | 2026-03-16
ROMP 09 LV SWITCHGEAR | CMH116ROMP09 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2026-03-16 | 2026-03-16
ROMP 09 LV SWITCHGEAR | CMH116ROMP09 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2026-03-16 | 2026-03-16
ROMP 09 LV SWITCHGEAR | CMH116ROMP09 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2026-03-16 | 2026-03-16
ROMP 10 LV SWITCHGEAR | CMH116ROMP10 | LV Switchgear | 1.5 | EATON | Marcella Bocciardi | 2026-07-06 | 2026-04-06 | 2026-04-06 | 2026-04-05 | 92 |  |  | Vendor confirmed pull-in request | Pull-In Ticket Completed |  | 91 | 2026-06-22
ROMP 10 LV SWITCHGEAR | CMH116ROMP10 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2026-04-06 | 2026-04-06
ROMP 10 LV SWITCHGEAR | CMH116ROMP10 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2026-04-06 | 2026-04-06
ROMP 10 LV SWITCHGEAR | CMH116ROMP10 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2026-04-06 | 2026-04-06
ROMP 10 LV SWITCHGEAR | CMH116ROMP10 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2026-04-06 | 2026-04-06
ROMP 10 LV SWITCHGEAR | CMH116ROMP10 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2026-04-06 | 2026-04-06
ROMP 10 LV SWITCHGEAR | CMH116ROMP10 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2026-04-06 | 2026-04-06
ROMP 11 LV SWITCHGEAR | CMH116ROMP11 | LV Switchgear | 2.6 | EATON | Marcella Bocciardi | 2026-07-27 | 2026-04-27 | 2026-04-27 | 2026-04-19 | 99 |  |  | Vendor confirmed pull-in request | Pull-In Ticket Completed |  | 91 | 2026-07-13
ROMP 11 LV SWITCHGEAR | CMH116ROMP11 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2026-04-27 | 2026-04-27
ROMP 11 LV SWITCHGEAR | CMH116ROMP11 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2026-04-27 | 2026-04-27
ROMP 11 LV SWITCHGEAR | CMH116ROMP11 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2026-04-27 | 2026-04-27
ROMP 11 LV SWITCHGEAR | CMH116ROMP11 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2026-04-27 | 2026-04-27
ROMP 11 LV SWITCHGEAR | CMH116ROMP11 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2026-04-27 | 2026-04-27
ROMP 11 LV SWITCHGEAR | CMH116ROMP11 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2026-04-27 | 2026-04-27
ROMP 12 LV SWITCHGEAR | CMH116ROMP12 | LV Switchgear | 1.6 | EATON | Marcella Bocciardi | 2026-08-17 | 2026-05-18 | 2026-05-18 | 2026-05-03 | 106 |  |  | Vendor confirmed pull-in request | Pull-In Ticket Completed |  | 91 | 2026-08-03
ROMP 12 LV SWITCHGEAR | CMH116ROMP12 | LV Switchgear | COP | EATON | Marcella Bocciardi |  | 2026-05-18 | 2026-05-18
ROMP 12 LV SWITCHGEAR | CMH116ROMP12 | LV Switchgear | USB | EATON | Marcella Bocciardi |  | 2026-05-18 | 2026-05-18
ROMP 12 LV SWITCHGEAR | CMH116ROMP12 | LV Switchgear | ATS | EATON | Marcella Bocciardi |  | 2026-05-18 | 2026-05-18
ROMP 12 LV SWITCHGEAR | CMH116ROMP12 | LV Switchgear | Meters & Relays | EATON | Marcella Bocciardi |  | 2026-05-18 | 2026-05-18
ROMP 12 LV SWITCHGEAR | CMH116ROMP12 | LV Switchgear | Panelboards | EATON | Marcella Bocciardi |  | 2026-05-18 | 2026-05-18
ROMP 12 LV SWITCHGEAR | CMH116ROMP12 | LV Switchgear | Transformers | EATON | Marcella Bocciardi |  | 2026-05-18 | 2026-05-18
MV SWITCHGEAR | [12 empty] | Going to PreFab
Phase 1 | CMH116ROMP01 | MV Switchgear | SWGR MV-A | EATON | Marcella Bocciardi | 2025-11-03 | 2025-09-08 | 2025-06-24 | 2025-06-24 | 171 | 2025-05-16 |  | At CWW |  |  | 132 | 2025-10-20
Phase 1 | CMH116ROMP01 | MV Switchgear | SWGR MV-B | EATON | Marcella Bocciardi | 2025-11-03 | 2025-09-08 | 2025-06-24 | 2025-06-24 | 171 | 2025-05-16 |  | At CWW |  |  | 132 | 2025-10-20
MV TRANSFORMER
Phase 1 |  | MV Transformers |  | EATON
ROMP 01 MV TRANSFORMER | CMH116ROMP01 | MV Transformers | HS-XFMR | EATON | Marcella Bocciardi | 2025-11-03 | 2025-08-20 | 2025-10-19 | 2025-10-19 | 14 | 2025-10-20 |  | 8/27/2025 Vendor has confirmed this delivery will arrive October 19th |  |  | 15 | 2025-10-20
ROMP 01 MV TRANSFORMER | CMH116ROMP01 | MV Transformers | USB 2.1A-XFMR | EATON | Marcella Bocciardi | 2025-11-03 | 2025-08-20 | 2025-10-19 | 2025-08-20 | 75 | 2025-08-20 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 15 | 2025-10-20
ROMP 01 MV TRANSFORMER | CMH116ROMP01 | MV Transformers | USB 2.1B-XFMR | EATON | Marcella Bocciardi | 2025-11-03 | 2025-08-20 | 2025-10-19 | 2025-08-20 | 75 | 2025-08-20 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 15 | 2025-10-20
ROMP 01 MV TRANSFORMER | CMH116ROMP01 | MV Transformers | USB 1.1C-XFMR | EATON | Marcella Bocciardi | 2025-11-03 | 2025-08-20 | 2025-10-19 | 2025-08-20 | 75 | 2025-08-20 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 15 | 2025-10-20
ROMP 01 MV TRANSFORMER | CMH116ROMP01 | MV Transformers | Fire Pump XMFR | EATON | Marcella Bocciardi | 2025-11-03 | 2025-08-20 | 2025-10-19 | TBD | 14 | 2025-10-20 |  | Ship date: 10/19; Vendor still awaits delivery date as of OFCI Meeting 9.15.2025 |  |  | 15 | 2025-10-20
Phase 2 |  | MV Transformers |  | EATON | [12 empty] | 2026-01-05
ROMP 02 MV TRANSFORMER | CMH116ROMP02 | MV Transformers | USB 1.1A-XFMR | EATON | Marcella Bocciardi | 2026-01-19 | 2025-08-21 | 2026-01-19 | 2025-08-21 | 151 | 2025-08-21 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-01-05
ROMP 02 MV TRANSFORMER | CMH116ROMP02 | MV Transformers | USB 1.1B-XFMR | EATON | Marcella Bocciardi | 2026-01-19 | 2025-08-21 | 2026-01-19 | 2025-08-21 | 151 | 2025-08-21 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-01-05
Phase 3 |  | MV Transformers |  | EATON | [12 empty] | 2026-01-26
ROMP 03 MV TRANSFORMER | CMH116ROMP03 | MV Transformers | USB 2.2A-XFMR | EATON | Marcella Bocciardi | 2026-02-09 | 2025-08-21 | 2026-02-09 | 2025-08-21 | 172 | 2025-08-21 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-01-26
ROMP 03 MV TRANSFORMER | CMH116ROMP03 | MV Transformers | USB 2.2B-XFMR | EATON | Marcella Bocciardi | 2026-02-09 | 2025-08-21 | 2026-02-09 | 2025-08-21 | 172 | 2025-08-21 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-01-26
Phase 4 |  | MV Transformers |  | EATON | [12 empty] | 2026-02-16
ROMP 04 MV TRANSFORMER | CMH116ROMP04 | MV Transformers | USB 1.2A-XFMR | EATON | Marcella Bocciardi | 2026-03-02 | 2025-08-21 | 2026-03-02 | 2025-08-21 | 193 | 2025-08-21 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-02-16
ROMP 04 MV TRANSFORMER | CMH116ROMP04 | MV Transformers | USB 1.2B-XFMR | EATON | Marcella Bocciardi | 2026-03-02 | 2025-08-22 | 2026-03-02 | 2025-08-22 | 192 | 2025-08-22 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-02-16
Phase 5 |  | MV Transformers |  | EATON | [12 empty] | 2026-03-09
ROMP 05 MV TRANSFORMER | CMH116ROMP05 | MV Transformers | USB 2.3A-XFMR | EATON | Marcella Bocciardi | 2026-03-23 | 2025-08-22 | 2026-03-23 | 2025-08-22 | 213 | 2025-08-22 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-03-09
ROMP 05 MV TRANSFORMER | CMH116ROMP05 | MV Transformers | USB 2.3B-XFMR | EATON | Marcella Bocciardi | 2026-03-23 | 2025-08-22 | 2026-03-23 | 2025-08-22 | 213 | 2025-08-22 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-03-09
Phase 6 |  | MV Transformers |  | EATON | [12 empty] | 2026-03-30
ROMP 06 MV TRANSFORMER | CMH116ROMP06 | MV Transformers | USB 1.3A-XFMR | EATON | Marcella Bocciardi | 2026-04-13 | 2025-08-22 | 2026-04-13 | 2025-08-22 | 234 | 2025-08-22 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-03-30
ROMP 06 MV TRANSFORMER | CMH116ROMP06 | MV Transformers | USB 1.3B-XFMR | EATON | Marcella Bocciardi | 2026-04-13 | 2025-08-22 | 2026-04-13 | 2025-08-22 | 234 | 2025-08-22 |  | Vendor has confirmed delivery of 15 transformers 5 units per day on August 20th, 21st and 22nd. |  |  | 0 | 2026-03-30
Phase 7 |  | MV Transformers |  | EATON | [12 empty] | 2026-04-20
ROMP 07 MV TRANSFORMER | CMH116ROMP07 | MV Transformers | USB 2.4A-XFMR | EATON | Marcella Bocciardi | 2026-05-04 | 2025-11-10 | 2026-02-04 | 2026-02-04 | 89 |  |  | OSD-26130 submitted 9/25 | Pull-In Ticket Rejected |  | 89 | 2026-04-20
ROMP 07 MV TRANSFORMER | CMH116ROMP07 | MV Transformers | USB 2.4B-XFMR | EATON | Marcella Bocciardi | 2026-05-04 | 2025-11-10 | 2026-02-04 | 2026-02-04 | 89 |  |  | OSD-26130 submitted 9/25 | Pull-In Ticket Rejected |  | 89 | 2026-04-20
ROMP 07 MV TRANSFORMER | CMH116ROMP07 | MV Transformers | USB 2.1C-XFMR | EATON | Marcella Bocciardi | 2026-05-04 | 2025-11-10 | 2026-02-04 | 2026-02-04 | 255 | 2025-08-22 |  |  |  |  | 89 | 2026-04-20
Phase 8 |  | MV Transformers |  | EATON | [12 empty] | 2026-05-11
ROMP 08 MV TRANSFORMER | CMH116ROMP08 | MV Transformers | USB 1.4A-XFMR | EATON | Marcella Bocciardi | 2026-05-25 | 2025-11-10 | 2026-02-04 | 2026-02-04 | 110 |  |  | OSD-26130 submitted 9/25 | Pull-In Ticket Rejected |  | 110 | 2026-05-11
ROMP 08 MV TRANSFORMER | CMH116ROMP08 | MV Transformers | USB 1.4B-XFMR | EATON | Marcella Bocciardi | 2026-05-25 | 2025-11-10 | 2026-02-04 | 2026-02-04 | 110 |  |  | OSD-26130 submitted 9/25 | Pull-In Ticket Rejected |  | 110 | 2026-05-11
Phase 9 |  | MV Transformers |  | EATON | [12 empty] | 2026-06-01
ROMP 09 MV TRANSFORMER | CMH116ROMP09 | MV Transformers | USB 2.5A-XFMR | EATON | Marcella Bocciardi | 2026-06-15 | 2025-11-10 | 2026-02-04 | 2026-02-04 | 131 |  |  | OSD-26130 submitted 9/25 | Pull-In Ticket Rejected |  | 131 | 2026-06-01
ROMP 09 MV TRANSFORMER | CMH116ROMP09 | MV Transformers | USB 2.5B-XFMR | EATON | Marcella Bocciardi | 2026-06-15 | 2025-11-10 | 2026-02-04 | 2026-02-04 | 131 |  |  | OSD-26130 submitted 9/25 | Pull-In Ticket Rejected |  | 131 | 2026-06-01
Phase 10 |  | MV Transformers |  | EATON | [12 empty] | 2026-06-22
ROMP 10 MV TRANSFORMER | CMH116ROMP10 | MV Transformers | USB 1.5A-XFMR | EATON | Marcella Bocciardi | 2026-07-06 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 152 |  |  | OSD-26131 submitted 9/25/2025 | Pull-In Ticket Rejected |  | 152 | 2026-06-22
ROMP 10 MV TRANSFORMER | CMH116ROMP10 | MV Transformers | USB 1.5B-XFMR | EATON | Marcella Bocciardi | 2026-07-06 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 152 |  |  | OSD-26131 submitted 9/25/2025 | Pull-In Ticket Rejected |  | 152 | 2026-06-22
Phase 11 |  | MV Transformers |  | EATON | [12 empty] | 2026-07-13
ROMP 11 MV TRANSFORMER | CMH116ROMP11 | MV Transformers | USB 2.6A-XFMR | EATON | Marcella Bocciardi | 2026-07-27 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 173 |  |  | OSD-26131 submitted 9/25/2025 | Pull-In Ticket Rejected |  | 173 | 2026-07-13
ROMP 11 MV TRANSFORMER | CMH116ROMP11 | MV Transformers | USB 2.6B-XFMR | EATON | Marcella Bocciardi | 2026-07-27 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 173 |  |  | OSD-26131 submitted 9/25/2025 | Pull-In Ticket Rejected |  | 173 | 2026-07-13
Phase 12 |  | MV Transformers |  | EATON | [12 empty] | 2026-08-03
ROMP 12 MV TRANSFORMER | CMH116ROMP12 | MV Transformers | USB 1.6A-XFMR | EATON | Marcella Bocciardi | 2026-08-17 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 194 |  |  | OSD-26131 submitted 9/25/2025 | Pull-In Ticket Rejected |  | 194 | 2026-08-03
ROMP 12 MV TRANSFORMER | CMH116ROMP12 | MV Transformers | USB 1.6B-XFMR | EATON | Marcella Bocciardi | 2026-08-17 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 194 |  |  | OSD-26131 submitted 9/25/2025 | Pull-In Ticket Rejected |  | 194 | 2026-08-03
BUSDUCT
ROMP 01 Busduct | CMH116ROMP01 | Busduct | 2.1 | SCHNEIDER ELECTRIC | Julie Florez | 2025-10-27 | 2025-09-22 | 2025-10-17 | 2026-01-20 | -85 |  |  | Dates for refabbed pieces 1/20/2026 | Pull-In Ticket Rejected |  | 10 | 2025-10-20
ROMP 02 Busduct | CMH116ROMP02 | Busduct | 1.1 | SCHNEIDER ELECTRIC | Julie Florez | 2026-01-12 | 2025-11-17 | 2026-01-05 | 2026-01-20 | -8 |  |  | Dates for refabbed pieces 1/20/2026 | Pull-In Ticket Rejected |  | 7 | 2026-01-05
ROMP 03 Busduct | CMH116ROMP03 | Busduct | 2.2 | SCHNEIDER ELECTRIC | Julie Florez | 2026-02-02 | 2025-12-08 | 2026-01-26 | 2026-01-26 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 01/26/2026 instead of 12/08/2025 | Pull-In Ticket Rejected |  | 7 | 2026-01-26
ROMP 04 Busduct | CMH116ROMP04 | Busduct | 1.2 | SCHNEIDER ELECTRIC | Julie Florez | 2026-02-23 | 2025-12-29 | 2026-02-16 | 2026-02-16 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 02/16/2026 instead of 12/29/2025 | Pull-In Ticket Rejected |  | 7 | 2026-02-16
ROMP 05 Busduct | CMH116ROMP05 | Busduct | 2.3 | SCHNEIDER ELECTRIC | Julie Florez | 2026-03-16 | 2026-01-19 | 2026-03-09 | 2026-03-09 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 03/09/2026 instead of 01/19/2026 | Pull-In Ticket Rejected |  | 7 | 2026-03-09
ROMP 06 Busduct | CMH116ROMP06 | Busduct | 1.3 | SCHNEIDER ELECTRIC | Julie Florez | 2026-04-06 | 2026-02-10 | 2026-03-30 | 2026-03-30 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 03/30/2026 instead of 02/10/2026 | Pull-In Ticket Rejected |  | 7 | 2026-03-30
ROMP 07 Busduct | CMH116ROMP07 | Busduct | 2.4 | SCHNEIDER ELECTRIC | Julie Florez | 2026-04-27 | 2026-03-22 | 2026-04-20 | 2026-04-20 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 04/20/2026 instead of 03/22/2026 | Pull-In Ticket Rejected |  | 7 | 2026-04-20
ROMP 08 Busduct | CMH116ROMP08 | Busduct | 1.4 | SCHNEIDER ELECTRIC | Julie Florez | 2026-05-18 | 2026-03-23 | 2026-05-11 | 2026-05-11 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 05/11/2026 instead of 03/23/2026 | Pull-In Ticket Rejected |  | 7 | 2026-05-11
ROMP 09 Busduct | CMH116ROMP09 | Busduct | 2.5 | SCHNEIDER ELECTRIC | Julie Florez | 2026-06-08 | 2026-04-13 | 2026-06-01 | 2026-06-01 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 06/01/2026 instead of 04/13/2026 | Pull-In Ticket Rejected |  | 7 | 2026-06-01
ROMP 10 Busduct | CMH116ROMP10 | Busduct | 1.5 | SCHNEIDER ELECTRIC | Julie Florez | 2026-06-29 | 2026-05-04 | 2026-06-22 | 2026-06-22 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 06/22/2026 instead of 05/04/2026 | Pull-In Ticket Rejected |  | 7 | 2026-06-22
ROMP 11 Busduct | CMH116ROMP11 | Busduct | 2.6 | SCHNEIDER ELECTRIC | Julie Florez | 2026-07-20 | 2026-05-25 | 2026-07-13 | 2026-07-13 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 07/13/2026 instead of 05/25/2026 | Pull-In Ticket Rejected |  | 7 | 2026-07-13
ROMP 12 Busduct | CMH116ROMP12 | Busduct | 1.6 | SCHNEIDER ELECTRIC | Julie Florez | 2026-08-10 | 2026-06-15 | 2026-08-03 | 2026-08-03 | 7 |  |  | New tickets are needed as of 8/15/2025. Ticket request was 08/03/2026 instead of 06/15/2026 | Pull-In Ticket Rejected |  | 7 | 2026-08-03
PDC
Phase 1 PDC | CMH116ROMP01 | PDC | 2.1 | FLEX | manasa.parthasarathy@flex.com | 2025-11-10 | 2025-09-18 | 2025-10-20 | 2025-11-10 | 0 | 2025-11-10 |  | 11/7/2025 Delivery from CWW to Prefab scheduled for 11/10/2025 10/2/2025-Potential QC issues identified on Flex PDC's. PAC Team is coordinating assessment. PAC was instructed to ensure delivery no later than ROS date per GC Prime Contract. If possible, PAC Team instructed to deliver by PAC EDD date, or somewhere in-between. (djtate) Onsite delivery request HC from CWW for 10/20/2025. Phase 1-10 have been delivered to Crane World Wide. | Pull-In Ticket Completed |  | 21 | 2025-10-20
Phase 2 PDC | CMH116ROMP02 | PDC | 1.1 | FLEX | manasa.parthasarathy@flex.com | 2026-01-26 | 2025-12-10 | 2025-12-10 | 2025-12-15 | 42 | 2025-12-15 |  | CWW was not able to deliver 12/10. 12/15 new date as agreed by Walbridge so both ROMPs 2 & 3 could be offloaded together. | Pull-In Ticket Requested |  | 47 | 2026-01-05
Phase 3 PDC | CMH116ROMP03 | PDC | 2.2 | FLEX | manasa.parthasarathy@flex.com | 2026-02-16 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 63 | 2025-12-15 |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-01-26
Phase 4 PDC | CMH116ROMP04 | PDC | 1.2 | FLEX | manasa.parthasarathy@flex.com | 2026-03-09 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-02-16
Phase 5 PDC | CMH116ROMP05 | PDC | 2.3 | FLEX | manasa.parthasarathy@flex.com | 2026-03-30 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-03-09
Phase 6 PDC | CMH116ROMP06 | PDC | 1.3 | FLEX | manasa.parthasarathy@flex.com | 2026-04-20 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-03-30
Phase 7 PDC | CMH116ROMP07 | PDC | 2.4 | FLEX | manasa.parthasarathy@flex.com | 2026-05-11 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-04-20
Phase 8 PDC | CMH116ROMP08 | PDC | 1.4 | FLEX | manasa.parthasarathy@flex.com | 2026-06-01 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-05-11
Phase 9 PDC | CMH116ROMP09 | PDC | 2.5 | FLEX | manasa.parthasarathy@flex.com | 2026-06-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-06-01
Phase 10 PDC | CMH116ROMP10 | PDC | 1.5 | FLEX | manasa.parthasarathy@flex.com | 2026-07-13 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-06-22
Phase 11 PDC | CMH116ROMP11 | PDC | 2.6 | FLEX | manasa.parthasarathy@flex.com | 2026-08-03 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-07-13
Phase 12 PDC | CMH116ROMP12 | PDC | 1.6 | FLEX | manasa.parthasarathy@flex.com | 2026-08-24 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 63 |  |  | Phase 1-10 have been delivered to Crane World Wide | Pull-In Ticket Requested |  | 63 | 2026-08-03
EXHAUST FANS
Phase 1 Exhaust Fan | CMH116ROMP01 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2025-11-03 | 2025-06-23 | 2025-07-24 | 2025-06-28 | 128 | 2025-06-28 |  | 5.8.25 - PAC/ACI resolved pull-in date discrepancies | Pull-In Ticket Completed |  | 102 | 2025-10-20
Phase 2 Exhaust Fan | CMH116ROMP02 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-01-19 | 2025-06-23 | 2025-07-24 | 2025-06-28 | 205 | 2025-06-28 |  | 5.8.25 - PAC/ACI resolved pull-in date discrepancies | Pull-In Ticket Completed |  | 179 | 2026-01-05
Phase 3 Exhaust Fan | CMH116ROMP03 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-02-09 | 2025-07-26 | 2025-07-26 | 2025-07-19 | 205 | 2025-07-19 |  | 5.8.25 - PAC/ACI resolved pull-in date discrepancies | Pull-In Ticket Completed |  | 198 | 2026-01-26
Phase 4 Exhaust Fan | CMH116ROMP04 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-03-02 | 2025-08-29 | 2025-07-26 | 2025-07-19 | 226 | 2025-07-19 |  | 5.8.25 - PAC/ACI resolved pull-in date discrepancies | Pull-In Ticket Completed |  | 219 | 2026-02-16
Phase 5 Exhaust Fan | CMH116ROMP05 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-03-23 | 2025-08-30 | 2025-08-30 | 2025-07-27 | 239 | 2025-07-27 |  | 5.8.25 - PAC/ACI resolved pull-in date discrepancies | Pull-In Ticket Completed |  | 205 | 2026-03-09
Phase 6 Exhaust Fan | CMH116ROMP06 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-04-13 | 2025-09-26 | 2025-08-30 | 2025-07-27 | 260 | 2025-07-27 |  | 5.8.25 - PAC/ACI resolved pull-in date discrepancies | Pull-In Ticket Completed |  | 226 | 2026-03-30
Phase 7 Exhaust Fan | CMH116ROMP07 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-05-04 | 2025-09-27 | 2025-09-27 | 2025-09-06 | 238 | 2025-09-08 |  | 8.14.25 Vendor and Poynter have agreed to pull this ROMP in. Pul-in ticket needed | Pull-In Ticket Completed |  | 219 | 2026-04-20
Phase 8 Exhaust Fan | CMH116ROMP08 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-05-25 | 2025-10-24 | 2025-09-27 | 2025-09-06 | 259 | 2025-09-08 |  | 8.14.25 Vendor and Poynter have agreed to pull this ROMP in. AWS Pull-in ticket needed. | Pull-In Ticket Completed |  | 240 | 2026-05-11
Phase 9 Exhaust Fan | CMH116ROMP09 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-06-15 | 2025-10-25 | 2025-10-25 | 2025-09-20 | 268 | 2025-09-20 |  | 8.14.25 Vendor and Poynter have agreed to pull this ROMP in. Pul-in ticket needed | Pull-In Ticket Completed |  | 233 | 2026-06-01
Phase 10 Exhaust Fan | CMH116ROMP10 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-07-06 | 2025-11-21 | 2025-10-25 | 2025-09-20 | 289 | 2025-09-20 |  | 8.14.25 Vendor and Poynter have agreed to pull this ROMP in. AWS Pull-in ticket needed. | Pull-In Ticket Completed |  | 254 | 2026-06-22
Phase 11 Exhaust Fan | CMH116ROMP11 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-07-27 | 2025-11-22 | 2025-11-22 | 2025-10-04 | 296 | 2025-10-04 |  | 8.14.25 Vendor and Poynter have agreed to pull this ROMP in. Pul-in ticket needed | Pull-In Ticket Completed |  | 247 | 2026-07-13
Phase 12 Exhaust Fan | CMH116ROMP12 | Exhaust Fan | ALL UNITS | ACI | Jack Roberts | 2026-08-17 | 2025-12-12 | 2025-11-22 | 2025-10-04 | 317 | 2025-10-04 |  | 8.14.25 Vendor and Poynter have agreed to pull this ROMP in. AWS Pull-in ticket needed. | Pull-In Ticket Completed |  | 268 | 2026-08-03
DAHU | [8 empty] | Offload Date
Phase 1 DAHU | CMH116ROMP01 | AHU | 2.1 | NORTEK | zachary.neels@nortek.com | 2025-11-03 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 82 | 2025-08-13 |  |  | Pull-In Ticket Completed |  | 82 | 2025-10-20
Phase 2 DAHU | CMH116ROMP02 | AHU | 1.1 | NORTEK | zachary.neels@nortek.com | 2026-01-19 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 131 | 2025-09-10 |  |  | Pull-In Ticket Completed |  | 131 | 2026-01-05
Phase 3 DAHU | CMH116ROMP03 | AHU | 2.2 | NORTEK | zachary.neels@nortek.com | 2026-02-09 | 2025-10-01 | 2025-10-01 | 2025-10-01 | 131 | 2025-10-01 |  |  | Pull-In Ticket Completed |  | 131 | 2026-01-26
Phase 4 DAHU | CMH116ROMP04 | AHU | 1.2 | NORTEK | zachary.neels@nortek.com | 2026-03-02 | 2025-10-22 | 2025-10-22 | 2025-10-30 | 123 | 2025-10-30 |  | Vendor did not fulfill 10/22/2025 and rescheduled for 10/30/2025 | Pull-In Ticket Completed |  | 131 | 2026-02-16
Phase 5 DAHU | CMH116ROMP05 | AHU | 2.3 | NORTEK | zachary.neels@nortek.com | 2026-03-23 | 2025-11-10 | 2025-11-10 | 2025-11-17 | 126 | 2025-11-17 |  | Vendor in progress to schedule ROMP 05 for 11.17.2025 | Pull-In Ticket Completed |  | 133 | 2026-03-09
Phase 6 DAHU | CMH116ROMP06 | AHU | 1.3 | NORTEK | zachary.neels@nortek.com | 2026-04-13 | 2025-11-20 | 2025-11-20 | 2025-11-19 | 145 | 2025-11-19 |  | Vendor in progress to schedule ROMP 06 for 11.19.2025 | Pull-In Ticket Completed |  | 144 | 2026-03-30
Phase 7 DAHU | CMH116ROMP07 | AHU | 2.4 | NORTEK | zachary.neels@nortek.com | 2026-05-04 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 152 | 2025-12-03 |  |  | Pull-In Ticket Completed |  | 152 | 2026-04-20
Phase 8 DAHU | CMH116ROMP08 | AHU | 1.4 | NORTEK | zachary.neels@nortek.com | 2026-05-25 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 164 | 2025-12-12 |  |  | Pull-In Ticket Completed |  | 164 | 2026-05-11
Phase 9 DAHU | CMH116ROMP09 | AHU | 2.5 | NORTEK | zachary.neels@nortek.com | 2026-06-15 | 2025-12-18 | 2025-12-18 | 2025-12-17 | 180 |  |  |  | Pull-In Ticket Completed |  | 179 | 2026-06-01
Phase 10 DAHU | CMH116ROMP10 | AHU | 1.5 | NORTEK | zachary.neels@nortek.com | 2026-07-06 | 2026-01-07 | 2026-01-15 | 2026-01-15 | 172 |  |  |  | Pull-In Ticket Completed |  | 172 | 2026-06-22
Phase 11 DAHU | CMH116ROMP11 | AHU | 2.6 | NORTEK | zachary.neels@nortek.com | 2026-07-27 | 2026-01-21 | 2026-01-27 | 2026-01-27 | 181 |  |  |  | Pull-In Ticket Completed |  | 181 | 2026-07-13
Phase 12 DAHU | CMH116ROMP12 | AHU | 1.6 | NORTEK | zachary.neels@nortek.com | 2026-08-17 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 194 |  |  |  | Pull-In Ticket Completed |  | 194 | 2026-08-03
AMCOP | [12 empty] | Going to PreFab
Phase 1 AMCOP | CMH116ROMP01 | AMCOP | 2.1 | INTERSTATES | craig.dewey@interstates.com | 2025-11-03 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 97 | 2025-07-29 |  |  | Pull-In Ticket Completed |  | 97 | 2025-10-20
Phase 2 AMCOP | CMH116ROMP02 | AMCOP | 1.1 | INTERSTATES | April Kruger | 2026-01-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | 153 | 2025-08-19 |  |  | Pull-In Ticket Completed |  | 153 | 2026-01-05
Phase 3 AMCOP | CMH116ROMP03 | AMCOP | 2.2 | INTERSTATES | Scott Shaw | 2026-02-09 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 139 | 2025-09-23 |  |  | Pull-In Ticket Completed |  | 139 | 2026-01-26
Phase 4 AMCOP | CMH116ROMP04 | AMCOP | 1.2 | INTERSTATES | craig.dewey@interstates.com | 2026-03-02 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 136 | 2025-10-17 |  | Vendor delivery to Prefab | Pull-In Ticket Completed |  | 132 | 2026-02-16
Phase 5 AMCOP | CMH116ROMP05 | AMCOP | 2.3 | INTERSTATES | April Kruger | 2026-03-23 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 125 | 2025-11-18 |  |  | Pull-In Ticket Completed |  | 125 | 2026-03-09
Phase 6 AMCOP | CMH116ROMP06 | AMCOP | 1.3 | INTERSTATES | Scott Shaw | 2026-04-13 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 118 | 2025-12-16 |  |  | Pull-In Ticket Completed |  | 118 | 2026-03-30
Phase 7 AMCOP | CMH116ROMP07 | AMCOP | 2.4 | INTERSTATES | craig.dewey@interstates.com | 2026-05-04 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 104 |  |  |  | Pull-In Ticket Completed |  | 104 | 2026-04-20
Phase 8 AMCOP | CMH116ROMP08 | AMCOP | 1.4 | INTERSTATES | April Kruger | 2026-05-25 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 90 |  |  |  | Pull-In Ticket Completed |  | 90 | 2026-05-11
Phase 9 AMCOP | CMH116ROMP09 | AMCOP | 2.5 | INTERSTATES | Scott Shaw | 2026-06-15 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 83 |  |  |  | Pull-In Ticket Completed |  | 83 | 2026-06-01
Phase 10 AMCOP | CMH116ROMP10 | AMCOP | 1.5 | INTERSTATES | craig.dewey@interstates.com | 2026-07-06 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 76 |  |  |  | Pull-In Ticket Completed |  | 76 | 2026-06-22
Phase 11 AMCOP | CMH116ROMP11 | AMCOP | 2.6 | INTERSTATES | April Kruger | 2026-07-27 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 69 |  |  |  | Pull-In Ticket Completed |  | 69 | 2026-07-13
Phase 12 AMCOP | CMH116ROMP12 | AMCOP | 1.6 | INTERSTATES | Scott Shaw | 2026-08-17 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 55 |  |  |  | Pull-In Ticket Completed |  | 55 | 2026-08-03
BACOP | [12 empty] | Going to PreFab
Phase 1 BACOP | CMH116ROMP01 | BACOP | 2.1 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2025-11-03 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 97 | 2025-07-29 |  |  | Pull-In Ticket Completed |  | 97 | 2025-10-20
Phase 2 BACOP | CMH116ROMP02 | BACOP | 1.1 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-01-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | 153 | 2025-08-19 |  |  | Pull-In Ticket Completed |  | 153 | 2026-01-05
Phase 3 BACOP | CMH116ROMP03 | BACOP | 2.2 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-02-09 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 137 | 2025-09-25 |  |  | Pull-In Ticket Completed |  | 139 | 2026-01-26
Phase 4 BACOP | CMH116ROMP04 | BACOP | 1.2 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-03-02 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 136 | 2025-10-17 |  |  | Pull-In Ticket Completed |  | 132 | 2026-02-16
Phase 5 BACOP | CMH116ROMP05 | BACOP | 2.3 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-03-23 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 125 | 2025-11-18 |  |  | Pull-In Ticket Completed |  | 125 | 2026-03-09
Phase 6 BACOP | CMH116ROMP06 | BACOP | 1.3 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-04-13 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 118 | 2025-12-16 |  |  | Pull-In Ticket Completed |  | 118 | 2026-03-30
Phase 7 BACOP | CMH116ROMP07 | BACOP | 2.4 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-05-04 | 2026-01-20 | 2026-01-20 | 2026-01-20 | 104 |  |  |  | Pull-In Ticket Completed |  | 104 | 2026-04-20
Phase 8 BACOP | CMH116ROMP08 | BACOP | 1.4 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-05-25 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 90 |  |  |  | Pull-In Ticket Completed |  | 90 | 2026-05-11
Phase 9 BACOP | CMH116ROMP09 | BACOP | 2.5 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-06-15 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 83 |  |  |  | Pull-In Ticket Completed |  | 83 | 2026-06-01
Phase 10 BACOP | CMH116ROMP10 | BACOP | 1.5 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-07-06 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 76 |  |  |  | Pull-In Ticket Completed |  | 76 | 2026-06-22
Phase 11 BACOP | CMH116ROMP11 | BACOP | 2.6 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-07-27 | 2026-05-19 | 2026-05-19 | 2026-05-19 | 69 |  |  |  | Pull-In Ticket Completed |  | 69 | 2026-07-13
Phase 12 BACOP | CMH116ROMP12 | BACOP | 1.6 | HANLEY ENERGY | mark.owens@hanleyenergy.com | 2026-08-17 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 55 |  |  |  | Pull-In Ticket Completed |  | 55 | 2026-08-03
PDC WHIPS | [12 empty] | Going to PreFab
Phase 1 PDC Whips | CMH116ROMP01 | PDC Whip | 2.1 | HARTING | Nora Valenzuela | 2025-11-10 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 53 | 2025-09-18 |  |  | Pull-In Ticket Completed |  | 53 | 2025-10-20
Phase 2 PDC Whips | CMH116ROMP02 | PDC Whip | 1.1 | HARTING | Marcelino Valdivia | 2026-01-26 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 102 | 2025-10-16 |  |  | Pull-In Ticket Completed |  | 102 | 2026-01-05
Phase 3 PDC Whips | CMH116ROMP03 | PDC Whip | 2.2 | HARTING | Nora Valenzuela | 2026-02-16 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 102 | 2025-11-06 |  |  | Pull-In Ticket Completed |  | 102 | 2026-01-26
Phase 4 PDC Whips | CMH116ROMP04 | PDC Whip | 1.2 | HARTING | Marcelino Valdivia | 2026-03-09 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 102 | 2025-11-27 |  | 11.24.25 - Walbridge requesting pushout to 12/4 due to Holiday | Pull-In Ticket Completed |  | 102 | 2026-02-16
Phase 5 PDC Whips | CMH116ROMP05 | PDC Whip | 2.3 | HARTING | Nora Valenzuela | 2026-03-30 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 102 |  |  |  | Pull-In Ticket Completed |  | 102 | 2026-03-09
Phase 6 PDC Whips | CMH116ROMP06 | PDC Whip | 1.3 | HARTING | Marcelino Valdivia | 2026-04-20 | 2025-12-22 | 2026-01-08 | 2026-01-08 | 102 |  |  | 11.3.25 - OSD-27697 created requesting pull-in to 12/22/25. | Pull-In Ticket In Progress |  | 102 | 2026-03-30
Phase 7 PDC Whips | CMH116ROMP07 | PDC Whip | 2.4 | HARTING | Nora Valenzuela | 2026-05-11 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 88 |  |  |  | Pull-In Ticket Completed |  | 88 | 2026-04-20
Phase 8 PDC Whips | CMH116ROMP08 | PDC Whip | 1.4 | HARTING | Marcelino Valdivia | 2026-06-01 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 88 |  |  |  | Pull-In Ticket Completed |  | 88 | 2026-05-11
Phase 9 PDC Whips | CMH116ROMP09 | PDC Whip | 2.5 | HARTING | Nora Valenzuela | 2026-06-22 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 88 |  |  |  | Pull-In Ticket Completed |  | 88 | 2026-06-01
Phase 10 PDC Whips | CMH116ROMP10 | PDC Whip | 1.5 | HARTING | Marcelino Valdivia | 2026-07-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 89 |  |  |  | Pull-In Ticket Completed |  | 89 | 2026-06-22
Phase 11 PDC Whips | CMH116ROMP11 | PDC Whip | 2.6 | HARTING | Nora Valenzuela | 2026-08-03 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 89 |  |  |  | Pull-In Ticket Completed |  | 89 | 2026-07-13
Phase 12 PDC Whips | CMH116ROMP12 | PDC Whip | 1.6 | HARTING | Marcelino Valdivia | 2026-08-24 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 89 |  |  |  | Pull-In Ticket Completed |  | 89 | 2026-08-03
UPS | [12 empty] | Going to PreFab
Phase 1 UPS | CMH116ROMP01 | UPS | 2.1 | MITSUBISHI | Dina Frigo | 2025-11-03 | 2025-08-28 | 2025-07-29 | 2025-08-28 | 67 | 2025-08-28 |  |  | Push-Out Ticket Completed |  | 97 | 2025-10-20
Phase 2 UPS | CMH116ROMP02 | UPS | 1.1 | MITSUBISHI | Kim Petry | 2026-01-19 | 2025-09-25 | 2025-08-19 | 2025-09-25 | 115 | 2025-09-26 |  | Actual Delivery Date Unknown: Missing QC Checklist as of 9/29/2025 | Push-Out Ticket Completed |  | 153 | 2026-01-05
Phase 3 UPS | CMH116ROMP03 | UPS | 2.2 | MITSUBISHI | Dina Frigo | 2026-02-09 | 2025-10-23 | 2025-09-23 | 2025-10-23 | 109 | 2025-10-23 |  |  | Push-Out Ticket Completed |  | 139 | 2026-01-26
Phase 4 UPS | CMH116ROMP04 | UPS | 1.2 | MITSUBISHI | Kim Petry | 2026-03-02 | 2025-11-20 | 2025-10-21 | 2025-11-20 | 97 | 2025-11-25 |  |  | Push-Out Ticket Completed |  | 132 | 2026-02-16
Phase 5 UPS | CMH116ROMP05 | UPS | 2.3 | MITSUBISHI | Dina Frigo | 2026-03-23 | 2025-12-18 | 2025-11-18 | 2025-12-18 | 95 |  |  |  | Push-Out Ticket Completed |  | 125 | 2026-03-09
Phase 6 UPS | CMH116ROMP06 | UPS | 1.3 | MITSUBISHI | Kim Petry | 2026-04-13 | 2026-01-15 | 2025-12-16 | 2026-01-15 | 88 |  |  |  | Push-Out Ticket Completed |  | 118 | 2026-03-30
Phase 7 UPS | CMH116ROMP07 | UPS | 2.4 | MITSUBISHI | Dina Frigo | 2026-05-04 | 2026-02-19 | 2026-01-20 | 2026-02-19 | 74 |  |  |  | Push-Out Ticket Completed |  | 104 | 2026-04-20
Phase 8 UPS | CMH116ROMP08 | UPS | 1.4 | MITSUBISHI | Kim Petry | 2026-05-25 | 2026-03-26 | 2026-02-24 | 2026-03-26 | 60 |  |  |  | Push-Out Ticket Completed |  | 90 | 2026-05-11
Phase 9 UPS | CMH116ROMP09 | UPS | 2.5 | MITSUBISHI | Dina Frigo | 2026-06-15 | 2026-04-23 | 2026-03-24 | 2026-04-23 | 53 |  |  |  | Push-Out Ticket Completed |  | 83 | 2026-06-01
Phase 10 UPS | CMH116ROMP10 | UPS | 1.5 | MITSUBISHI | Kim Petry | 2026-07-06 | 2026-05-21 | 2026-04-21 | 2026-05-21 | 46 |  |  |  | Push-Out Ticket Completed |  | 76 | 2026-06-22
Phase 11 UPS | CMH116ROMP11 | UPS | 2.6 | MITSUBISHI | Dina Frigo | 2026-07-27 | 2026-06-18 | 2026-05-19 | 2026-06-18 | 39 |  |  |  | Push-Out Ticket Completed |  | 69 | 2026-07-13
Phase 12 UPS | CMH116ROMP12 | UPS | 1.6 | MITSUBISHI | Kim Petry | 2026-08-17 | 2026-07-23 | 2026-06-23 | 2026-07-23 | 25 |  |  |  | Push-Out Ticket Completed |  | 55 | 2026-08-03
RACKING
Phase 1 Racking | CMH116ROMP01 | Racking | 2.1 | STAR NOVA | Houpu XU | 2025-10-27 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 74 | 2025-08-14 |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 74 | 2025-10-20 | 2025-10-19
Phase 2 Racking | CMH116ROMP02 | Racking | 1.1 | STAR NOVA | Houpu XU | 2026-01-12 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 123 | 2025-09-11 |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 123 | 2026-01-05 | 2026-01-05
Phase 3 Racking | CMH116ROMP03 | Racking | 2.2 | STAR NOVA | Houpu XU | 2026-02-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 123 | 2025-10-02 |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 123 | 2026-01-26 | 2026-01-26
Phase 4 Racking | CMH116ROMP04 | Racking | 1.2 | STAR NOVA | Houpu XU | 2026-02-23 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 123 | 2025-10-23 |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 123 | 2026-02-16 | 2026-02-16
Phase 5 Racking | CMH116ROMP05 | Racking | 2.3 | STAR NOVA | Houpu XU | 2026-03-16 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 123 | 2025-11-13 |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 123 | 2026-03-09 | 2026-03-09
Phase 6 Racking | CMH116ROMP06 | Racking | 1.3 | STAR NOVA | Houpu XU | 2026-04-06 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 123 | 2025-12-04 |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 123 | 2026-03-30 | 2026-03-30
Phase 7 Racking | CMH116ROMP07 | Racking | 2.4 | STAR NOVA | Houpu XU | 2026-04-27 | 2026-01-08 | 2026-01-08 | 2026-01-08 | 109 |  |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 109 | 2026-04-20 | 2026-04-20
Phase 8 Racking | CMH116ROMP08 | Racking | 1.4 | STAR NOVA | Houpu XU | 2026-05-18 | 2026-01-29 | 2026-01-29 | 2026-01-29 | 109 |  |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 109 | 2026-05-11 | 2026-05-11
Phase 9 Racking | CMH116ROMP09 | Racking | 2.5 | STAR NOVA | Houpu XU | 2026-06-08 | 2026-02-19 | 2026-02-19 | 2026-02-19 | 109 |  |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 109 | 2026-06-01 | 2026-06-01
Phase 10 Racking | CMH116ROMP10 | Racking | 1.5 | STAR NOVA | Houpu XU | 2026-06-29 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 110 |  |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 110 | 2026-06-22 | 2026-06-22
Phase 11 Racking | CMH116ROMP11 | Racking | 2.6 | STAR NOVA | Houpu XU | 2026-07-20 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 110 |  |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 110 | 2026-07-13 | 2026-07-13
Phase 12 Racking | CMH116ROMP12 | Racking | 1.6 | STAR NOVA | Houpu XU | 2026-08-10 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 110 |  |  | 5.12.25 - New delivery dates per Walid email | Pull-In Ticket Completed |  | 110 | 2026-08-03 | 2026-08-03

## Comments
Row 80 | HSSB delivery to Prefab 12/15 | Jason Laird | 12/05/25 7:07 AM
Row 92 | Is there an estimated delivery date for the ATS equipment. | Jason Laird | 12/05/25 6:43 AM
Sheet | @alepar@hilscher-clarke.com | Jason Laird | 12/05/25 10:49 AM

## Summary
# of Items Overdue on build | 10
Current # of Milestone Blockers | 0
AVG rOSD for GEN's | 92.549
ROLLS-ROYCE - ROMP01 Generator | -21
ROLLS-ROYCE - ROMP02 Generator | 54
ROLLS-ROYCE - ROMP03 Generator | 69
ROLLS-ROYCE - ROMP04 Generator | 90
ROLLS-ROYCE - ROMP05 Generator | 98
ROLLS-ROYCE - ROMP06 Generator | 119
ROLLS-ROYCE - ROMP07 Generator | 89
ROLLS-ROYCE - ROMP08 Generator | 110
ROLLS-ROYCE - ROMP09 Generator | 109
ROLLS-ROYCE - ROMP10 Generator | 109
ROLLS-ROYCE - ROMP11 Generator | 116
ROLLS-ROYCE - ROMP12 Generator | 130
EATON- ROMP01 LV Switchgear | -18
EATON- ROMP02 LV Switchgear | 59
EATON- ROMP03 LV Switchgear | 105
EATON- ROMP04 LV Switchgear | 57
EATON- ROMP05 LV Switchgear | 57
EATON- ROMP06 LV Switchgear | 64
EATON- ROMP07 LV Switchgear | 71
EATON- ROMP08 LV Switchgear | 78
EATON- ROMP09 LV Switchgear | 85
EATON- ROMP10 LV Switchgear | 92
EATON- ROMP11 LV Switchgear | 99
EATON- ROMP12 LV Switchgear | 106
EATON- ROMP01 MV Switchgear | 171
EATON- ROMP01 MV Transformers | 14
EATON- ROMP02 MV Transformers | 151
EATON- ROMP03 MV Transformers | 172
EATON- ROMP04 MV Transformers | 192
EATON- ROMP05 MV Transformers | 213
EATON- ROMP06 MV Transformers | 0
EATON- ROMP07 MV Transformers | 0
EATON- ROMP08 MV Transformers | 0
EATON- ROMP09 MV Transformers | 0
EATON- ROMP10 MV Transformers | 152
EATON- ROMP11 MV Transformers | 173
EATON- ROMP12 MV Transformers | 194
SCHNEIDER ELECTRIC- ROMP01 Busduct | -85
SCHNEIDER ELECTRIC- ROMP02 Busduct | -8
SCHNEIDER ELECTRIC- ROMP03 Busduct | 7
SCHNEIDER ELECTRIC- ROMP04 Busduct | 7
SCHNEIDER ELECTRIC- ROMP05 Busduct | 7
SCHNEIDER ELECTRIC- ROMP06 Busduct | 7
SCHNEIDER ELECTRIC- ROMP07 Busduct | 7
SCHNEIDER ELECTRIC- ROMP08 Busduct | 7
SCHNEIDER ELECTRIC- ROMP09 Busduct | 7
SCHNEIDER ELECTRIC- ROMP10 Busduct | 7
SCHNEIDER ELECTRIC- ROMP11 Busduct | 7
SCHNEIDER ELECTRIC- ROMP12 Busduct | 7
TETRIS- ROMP01 PDC | 0
TETRIS- ROMP02 PDC | 0
TETRIS- ROMP03 PDC | 0
TETRIS- ROMP04 PDC | 0
TETRIS- ROMP5 PDC | 0
TETRIS- ROMP6 PDC | 0
TETRIS- ROMP07 PDC | 0
TETRIS- ROMP08 PDC | 0
TETRIS- ROMP09 PDC | 0
TETRIS- ROMP10 PDC | 0
TETRIS- ROMP11 PDC | 0
TETRIS- ROMP12 PDC | 0
ACI- ROMP01 Exhaust Fan | 128
ACI- ROMP02 Exhaust Fan | 205
ACI- ROMP03 Exhaust Fan | 205
ACI- ROMP04 Exhaust Fan | 226
ACI- ROMP05 Exhaust Fan | 239
ACI- ROMP06 Exhaust Fan | 260
ACI- ROMP07 Exhaust Fan | 238
ACI- ROMP08 Exhaust Fan | 259
ACI- ROMP09 Exhaust Fan | 268
ACI- ROMP10 Exhaust Fan | 289
ACI- ROMP11 Exhaust Fan | 296
ACI- ROMP12 Exhaust Fan | 317
NORTEK- ROMP01 DHAU | 82
NORTEK- ROMP02 DHAU | 131
NORTEK- ROMP03 DHAU | 131
NORTEK- ROMP04 DHAU | 123
NORTEK- ROMP05 DHAU | 126
NORTEK- ROMP06 DHAU | 145
NORTEK- ROMP07 DHAU | 152
NORTEK- ROMP08 DHAU | 164
NORTEK- ROMP09 DHAU | 180
NORTEK- ROMP10 DHAU | 172
NORTEK- ROMP11 DHAU | 181
NORTEK- ROMP12 DHAU | 194
INTERSTATES- ROMP01 AMCOP | 97
INTERSTATES- ROMP02 AMCOP | 153
INTERSTATES- ROMP03 AMCOP | 139
INTERSTATES- ROMP04 AMCOP | 136
INTERSTATES- ROMP05 AMCOP | 125
INTERSTATES- ROMP06 AMCOP | 118
INTERSTATES- ROMP07 AMCOP | 104
INTERSTATES- ROMP08 AMCOP | 90
INTERSTATES- ROMP09 AMCOP | 83
INTERSTATES- ROMP10 AMCOP | 76
INTERSTATES- ROMP11 AMCOP | 69
INTERSTATES- ROMP12 AMCOP | 55
HANLEY ENERGY-ROMP01 BACOP | 97
HANLEY ENERGY-ROMP02 BACOP | 153
HANLEY ENERGY-ROMP03 BACOP | 137
HANLEY ENERGY-ROMP04 BACOP | 136
HANLEY ENERGY-ROMP05 BACOP | 125
HANLEY ENERGY-ROMP06 BACOP | 118
HANLEY ENERGY-ROMP07 BACOP | 104
HANLEY ENERGY-ROMP08 BACOP | 90
HANLEY ENERGY-ROMP09 BACOP | 83
HANLEY ENERGY-ROMP10 BACOP | 76
HANLEY ENERGY-ROMP11 BACOP | 69
HANLEY ENERGY-ROMP12 BACOP | 55
HARTING-ROMP01 PDC Whip | 53
HARTING-ROMP02 PDC Whip | 102
HARTING-ROMP03 PDC Whip | 102
HARTING-ROMP04 PDC Whip | 102
HARTING-ROMP05 PDC Whip | 102
HARTING-ROMP06 PDC Whip | 102
HARTING-ROMP07 PDC Whip | 88
HARTING-ROMP08 PDC Whip | 88
HARTING-ROMP09 PDC Whip | 88
HARTING-ROMP10 PDC Whip | 89
HARTING-ROMP11 PDC Whip | 89
HARTING-ROMP12 PDC Whip | 89
MITSUBISHI-ROMP01 UPS | 67
MITSUBISHI-ROMP02 UPS | 115
MITSUBISHI-ROMP03 UPS | 109
MITSUBISHI-ROMP04 UPS | 97
MITSUBISHI-ROMP05 UPS | 95
MITSUBISHI-ROMP06 UPS | 88
MITSUBISHI-ROMP07 UPS | 74
MITSUBISHI-ROMP08 UPS | 60
MITSUBISHI-ROMP09 UPS | 53
MITSUBISHI-ROMP10 UPS | 46
MITSUBISHI-ROMP11 UPS | 39
MITSUBISHI-ROMP12 UPS | 25
STAR NOVA-ROMP01 Racking | 74
STAR NOVA-ROMP02 Racking | 123
STAR NOVA-ROMP03 Racking | 123
STAR NOVA-ROMP04 Racking | 123
STAR NOVA-ROMP05 Racking | 123
STAR NOVA-ROMP06 Racking | 123
STAR NOVA-ROMP07 Racking | 109
STAR NOVA-ROMP08 Racking | 109
STAR NOVA-ROMP09 Racking | 109
STAR NOVA-ROMP10 Racking | 110
STAR NOVA-ROMP11 Racking | 110
STAR NOVA-ROMP12 Racking | 110