## 03. CMH120 OFCI Log REV2.0
OFCI Equipment Category | AWS FBN | LLE Type | Unit Tag | Vendor | Vendor Contact | PAC EDD | Vendor On Site Delivery Date | Required On Site per GC Prime Contract | Date Requested for Tickets | ROSD Check | Actual Delivery Date | Milestone Blockers? | Notes | Push/Pull Tickets | Ticket Link | GC Contractual Start Work Date
GENERATORS
Phase 1 | [8 empty] | 2025-12-17 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 GENERATOR | CMH120ROMP01 | Generator | GEN 2.1A | ROLLS-ROYCE | Madison Savary | 2026-02-09 | 2026-02-09 | 2026-02-23 | 2025-12-17 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 GENERATOR | CMH120ROMP01 | Generator | GEN 2.1B | ROLLS-ROYCE | Matt Schulz | 2026-02-09 | 2026-02-09 | 2026-02-23 | 2025-12-17 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 GENERATOR | CMH120ROMP01 | Generator | GEN 1.1C | ROLLS-ROYCE | Madison Savary | 2026-02-09 | 2026-02-09 | 2026-02-23 | 2025-12-17 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 GENERATOR | CMH120ROMP01 | Generator | GEN 2.1C | ROLLS-ROYCE | Madison Savary | 2026-02-09 | 2026-02-09 |  | 2025-12-17
ROMP 01 GENERATOR | CMH120ROMP01 | Generator | Gen House | ROLLS-ROYCE | Madison Savary | 2026-02-09 | 2026-02-09 |  | 2025-12-17
ROMP01 SCR | CMH120ROMP01 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-02-09 | 2026-02-09 | 2026-02-23 | 2025-12-17 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP01 LOOSE PARTS | CMH120ROMP01 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-02-09 | 2026-02-09 | 2026-02-23 | 2025-12-17 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
Phase 2 | [8 empty] | 2026-02-10 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 GENERATOR | CMH120ROMP02 | Generator | GEN 1.1A | ROLLS-ROYCE | Madison Savary | 2026-04-27 | 2026-04-27 | 2026-05-11 | 2026-02-10 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 GENERATOR | CMH120ROMP02 | Generator | GEN 1.1B | ROLLS-ROYCE | Matt Schulz | 2026-04-27 | 2026-04-27 | 2026-05-11 | 2026-02-10 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP02 SCR | CMH120ROMP02 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-04-27 | 2026-05-05 | 2026-05-11 | 2026-02-10 | 6 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP02 LOOSE PARTS | CMH120ROMP02 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-04-27 | 2026-04-22 | 2026-05-11 | 2026-02-10 | 19 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
Phase 3 | [8 empty] | 2026-04-16 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 GENERATOR | CMH120ROMP03 | Generator | GEN 2.2A | ROLLS-ROYCE | Madison Savary | 2026-04-16 | 2026-04-16 | 2026-06-08 | 2026-04-16 | 53 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 GENERATOR | CMH120ROMP03 | Generator | GEN 2.2B | ROLLS-ROYCE | Matt Schulz | 2026-04-16 | 2026-04-16 | 2026-06-08 | 2026-04-16 | 53 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP03 SCR | CMH120ROMP03 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-04-16 | 2026-04-16 | 2026-06-08 | 2026-04-16 | 53 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP03 LOOSE PARTS | CMH120ROMP03 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-04-16 | 2026-04-16 | 2026-06-08 | 2026-04-16 | 53 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
Phase 4 | [8 empty] | 2026-03-18 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 GENERATOR | CMH120ROMP04 | Generator | GEN 1.2A | ROLLS-ROYCE | Madison Savary | 2026-05-08 | 2026-05-08 | 2026-07-06 | 2026-03-18 | 59 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 GENERATOR | CMH120ROMP04 | Generator | GEN 1.2B | ROLLS-ROYCE | Matt Schulz | 2026-05-08 | 2026-05-08 | 2026-07-06 | 2026-03-18 | 59 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP04 SCR | CMH120ROMP04 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-05-08 | 2026-05-08 | 2026-07-06 | 2026-03-18 | 59 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP04 LOOSE PARTS | CMH120ROMP04 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-05-08 | 2026-05-08 | 2026-07-06 | 2026-03-18 | 59 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
Phase 5 | [13 empty] | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 GENERATOR | CMH120ROMP05 | Generator | GEN 2.3A | ROLLS-ROYCE | Madison Savary | 2026-05-15 | 2026-05-15 | 2026-08-03 | 2026-06-25 | 80 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 GENERATOR | CMH120ROMP05 | Generator | GEN 2.3B | ROLLS-ROYCE | Matt Schulz | 2026-05-15 | 2026-05-15 | 2026-08-03 | 2026-06-25 | 80 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP05 SCR | CMH120ROMP05 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-05-15 | 2026-05-15 | 2026-08-03 | 2026-06-25 | 80 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP05 LOOSE PARTS | CMH120ROMP05 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-05-15 | 2026-05-15 | 2026-08-03 | 2026-06-25 | 80 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
Phase 6 | [13 empty] | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 GENERATOR | CMH120ROMP06 | Generator | GEN 1.3A | ROLLS-ROYCE | Madison Savary | 2026-05-21 | 2026-05-21 | 2026-08-31 | 2026-05-21 | 102 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 GENERATOR | CMH120ROMP06 | Generator | GEN 1.3B | ROLLS-ROYCE | Matt Schulz | 2026-05-21 | 2026-05-21 | 2026-08-31 | 2026-05-21 | 102 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP06 SCR | CMH120ROMP06 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-05-21 | 2026-05-21 | 2026-08-31 | 2026-05-21 | 102 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP06 LOOSE PARTS | CMH120ROMP06 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-05-21 | 2026-05-21 | 2026-08-31 | 2026-05-21 | 102 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
Phase 7 | [13 empty] | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 GENERATOR | CMH120ROMP07 | Generator | GEN 2.4A | ROLLS-ROYCE | Madison Savary | 2026-06-23 | 2026-06-23 | 2026-09-28 | 2026-08-20 | 97 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 GENERATOR | CMH120ROMP07 | Generator | GEN 2.4B | ROLLS-ROYCE | Matt Schulz | 2026-06-23 | 2026-06-23 | 2026-09-28 | 2026-08-20 | 97 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 GENERATOR | CMH120ROMP07 | Generator | GEN 2.1C | ROLLS-ROYCE | Madison Savary | 2026-06-23 | 2026-06-23 | 2026-09-28 | 2026-08-20 | 97 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP07 SCR | CMH120ROMP07 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-06-23 | 2026-06-23 | 2026-09-28 | 2026-08-20 | 97 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP07 LOOSE PARTS | CMH120ROMP07 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-06-23 | 2026-06-23 | 2026-09-28 | 2026-08-20 | 97 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
Phase 8 | [13 empty] | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 GENERATOR | CMH120ROMP08 | Generator | GEN 1.4A | ROLLS-ROYCE | Madison Savary | 2026-07-10 | 2026-07-10 | 2026-10-26 | 2026-07-23 | 108 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 GENERATOR | CMH120ROMP08 | Generator | GEN 1.4B | ROLLS-ROYCE | Matt Schulz | 2026-07-10 | 2026-07-10 | 2026-10-26 | 2026-07-23 | 108 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP08 SCR | CMH120ROMP08 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-07-10 | 2026-07-10 | 2026-10-26 | 2026-07-23 | 108 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP08 LOOSE PARTS | CMH120ROMP08 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-07-10 | 2026-07-10 | 2026-10-26 | 2026-07-23 | 108 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
Phase 9 | [13 empty] | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 GENERATOR | CMH120ROMP09 | Generator | GEN 2.3A | ROLLS-ROYCE | Madison Savary | 2026-07-24 | 2026-07-24 | 2026-11-23 | 2026-10-15 | 122 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 GENERATOR | CMH120ROMP09 | Generator | GEN 2.3B | ROLLS-ROYCE | Matt Schulz | 2026-07-24 | 2026-07-24 | 2026-11-23 | 2026-10-15 | 122 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP09 SCR | CMH120ROMP09 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-07-24 | 2026-07-24 | 2026-11-23 | 2026-10-15 | 122 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP09 LOOSE PARTS | CMH120ROMP09 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-07-24 | 2026-07-24 | 2026-11-23 | 2026-10-15 | 122 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
Phase 10 | [13 empty] | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 GENERATOR | CMH120ROMP10 | Generator | GEN 2.5A | ROLLS-ROYCE | Madison Savary | 2026-08-07 | 2026-08-07 | 2026-12-21 | 2026-09-17 | 136 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 GENERATOR | CMH120ROMP10 | Generator | GEN 2.5B | ROLLS-ROYCE | Matt Schulz | 2026-08-07 | 2026-08-07 | 2026-12-21 | 2026-09-17 | 136 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP10 SCR | CMH120ROMP10 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-08-07 | 2026-08-07 | 2026-12-21 | 2026-09-17 | 136 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP10 LOOSE PARTS | CMH120ROMP10 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-08-07 | 2026-08-07 | 2026-12-21 | 2026-09-17 | 136 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
Phase 11 | [13 empty] | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 GENERATOR | CMH120ROMP11 | Generator | GEN 2.6A | ROLLS-ROYCE | Madison Savary | 2026-08-21 | 2026-08-21 | 2027-01-18 | 2026-12-10 | 150 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 GENERATOR | CMH120ROMP11 | Generator | GEN 2.6B | ROLLS-ROYCE | Matt Schulz | 2026-08-21 | 2026-08-21 | 2027-01-18 | 2026-12-10 | 150 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP11 SCR | CMH120ROMP11 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-08-21 | 2026-08-21 | 2027-01-18 | 2026-12-10 | 150 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP11 LOOSE PARTS | CMH120ROMP11 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-08-21 | 2026-08-21 | 2027-01-18 | 2026-12-10 | 150 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
Phase 12 | [13 empty] | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 GENERATOR | CMH120ROMP12 | Generator | GEN 1.6A | ROLLS-ROYCE | Madison Savary | 2026-09-04 | 2026-09-04 | 2027-02-15 | 2026-11-12 | 164 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 GENERATOR | CMH120ROMP12 | Generator | GEN 1.6B | ROLLS-ROYCE | Matt Schulz | 2026-09-04 | 2026-09-04 | 2027-02-15 | 2026-11-12 | 164 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP12 SCR | CMH120ROMP12 | Generator | ALL UNITS | ROLLS-ROYCE | Madison Savary | 2026-09-04 | 2026-09-04 | 2027-02-15 | 2026-11-12 | 164 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP12 LOOSE PARTS | CMH120ROMP12 | Generator | ALL UNITS | ROLLS-ROYCE | Matt Schulz | 2026-09-04 | 2026-09-04 | 2027-02-15 | 2026-11-12 | 164 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
MV SWITCHGEAR
ROMP 01 MV SWITCHGEAR | CMH120ROMP01 | MV Switchgear | SWGR MV-A | IEM | Joseph Molnar | 2025-12-08 | 2025-12-08 | 2026-02-16 | 2025-12-08 | 69 | 2025-12-09 |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 MV SWITCHGEAR | CMH120ROMP01 | MV Switchgear | SWGR MV-B | IEM | Joseph Molnar | 2025-12-08 | 2025-12-10 | 2026-02-16 | 2025-12-08 | 68 | 2025-12-10 |  |  | Pull-In Ticket Requested |  | 2026-02-02
MV TRANSFORMER
Phase 1 | [8 empty] | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 MV TRANSFORMER | CMH120ROMP01 | MV Transformers | FP-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-16 | 2026-02-16 | 2026-01-05 | 31 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 MV TRANSFORMER | CMH120ROMP01 | MV Transformers | HSSB-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-03-27 | 2026-02-16 | 2026-01-05 | -39 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 MV TRANSFORMER | CMH120ROMP01 | MV Transformers | USB 2.1A-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-16 | 2026-02-16 | 2026-01-05 | 31 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 MV TRANSFORMER | CMH120ROMP01 | MV Transformers | USB 2.1B-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-16 | 2026-02-16 | 2026-01-05 | 31 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 MV TRANSFORMER | CMH120ROMP01 | MV Transformers | USB 2.1C-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-16 | 2026-02-16 | 2026-01-05 | 31 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 MV TRANSFORMER | CMH120ROMP01 | MV Transformers | USB 1.1C-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-16 | 2026-02-16 | 2026-01-05 | 31 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
Phase 2 | [8 empty] | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 MV TRANSFORMER | CMH120ROMP02 | MV Transformers | USB-XMFR 1.1A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-30 | 2026-05-04 | 2026-01-05 | 94 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 MV TRANSFORMER | CMH120ROMP02 | MV Transformers | USB-XFMR 1.1B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-30 | 2026-05-04 | 2026-01-05 | 94 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
Phase 3 | [8 empty] | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 MV TRANSFORMER | CMH120ROMP03 | MV Transformers | USB 2.2A-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-30 | 2026-06-01 | 2026-01-05 | 122 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 MV TRANSFORMER | CMH120ROMP03 | MV Transformers | USB 2.2B-XFMR | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-30 | 2026-06-01 | 2026-01-05 | 122 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
Phase 4 | [8 empty] | 2026-04-27 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 MV TRANSFORMER | CMH120ROMP04 | MV Transformers | USB-XFMR 1.2A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-01-30 | 2026-06-29 | 2026-04-27 | 150 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 MV TRANSFORMER | CMH120ROMP04 | MV Transformers | USB-XFMR 1.2B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-02-13 | 2026-06-29 | 2026-04-27 | 136 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
Phase 5 | [8 empty] | 2026-04-27 |  |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 MV TRANSFORMER | CMH120ROMP05 | MV Transformers | USB-XFMR 2.3A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-02-13 | 2026-07-27 | 2026-04-27 | 164 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 MV TRANSFORMER | CMH120ROMP05 | MV Transformers | USB-XFMR 2.3B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-02-13 | 2026-07-27 | 2026-04-27 | 164 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
Phase 6 | [8 empty] | 2026-04-27 |  |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 MV TRANSFORMER | CMH120ROMP06 | MV Transformers | USB-XFMR 1.3A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-02-27 | 2026-08-24 | 2026-04-27 | 178 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 MV TRANSFORMER | CMH120ROMP06 | MV Transformers | USB-XFMR 1.3B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-02-27 | 2026-08-24 | 2026-04-27 | 178 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
Phase 7 | [8 empty] | 2026-04-27 |  |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 MV TRANSFORMER | CMH120ROMP07 | MV Transformers | USB-XFMR 2.4A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-08-31 | 2026-09-21 | 2026-04-27 | 21 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 MV TRANSFORMER | CMH120ROMP07 | MV Transformers | USB-XFMR 2.4B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-08-31 | 2026-09-21 | 2026-04-27 | 21 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
Phase 8 | [8 empty] | 2026-07-20 |  |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 MV TRANSFORMER | CMH120ROMP08 | MV Transformers | USB-XFMR 1.4A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-08-31 | 2026-10-19 | 2026-07-20 | 49 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 MV TRANSFORMER | CMH120ROMP08 | MV Transformers | USB-XFMR 1.4B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-08-31 | 2026-10-19 | 2026-07-20 | 49 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
Phase 9 | [8 empty] | 2026-07-20 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 MV TRANSFORMER | CMH120ROMP09 | MV Transformers | USB-XFMR 2.5A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-08-31 | 2026-11-16 | 2026-07-20 | 77 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 MV TRANSFORMER | CMH120ROMP09 | MV Transformers | USB-XFMR 2.5B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-08-31 | 2026-11-16 | 2026-07-20 | 77 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
Phase10 | [8 empty] | 2026-07-20 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 MV TRANSFORMER | CMH120ROMP10 | MV Transformers | USB-XFMR 1.5A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-09-30 | 2026-12-14 | 2026-07-20 | 75 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 MV TRANSFORMER | CMH120ROMP10 | MV Transformers | USB-XFMR 1.5B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-09-30 | 2026-12-14 | 2026-07-20 | 75 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
Phase 11 | [8 empty] | 2026-07-20 |  |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 MV TRANSFORMER | CMH120ROMP11 | MV Transformers | USB-XFMR 2.6A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-09-30 | 2027-01-11 | 2026-07-20 | 103 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 MV TRANSFORMER | CMH120ROMP11 | MV Transformers | USB-XFMR 2.6B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-09-30 | 2027-01-11 | 2026-07-20 | 103 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
Phase 12 | [8 empty] | 2026-07-20 |  |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 MV TRANSFORMER | CMH120ROMP12 | MV Transformers | USB-XFMR 1.6A | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-09-30 | 2027-02-08 | 2026-07-20 | 131 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 MV TRANSFORMER | CMH120ROMP12 | MV Transformers | USB-XFMR 1.6B | Hitachi Energy | andrew.adams@hitachienergy.com |  | 2026-09-30 | 2027-02-08 | 2026-07-20 | 131 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
BUSDUCT
Phase 1 | CMH120ROMP01 | Busduct | 2.1 | VERTIV | Nina Chibani | 2026-01-05 | 2026-02-23 | 2026-02-09 | 2026-01-05 | -14 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
Phase 2 | CMH120ROMP02 | Busduct | 1.1 | VERTIV | Nina Chibani | 2026-03-02 | 2026-03-09 | 2026-04-27 | 2026-03-02 | 49 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
Phase 3 | CMH120ROMP03 | Busduct | 2.2 | VERTIV | Nina Chibani | 2026-03-30 | 2026-03-23 | 2026-05-25 | 2026-03-30 | 63 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
Phase 4 | CMH120ROMP04 | Busduct | 1.2 | VERTIV | Nina Chibani | 2026-04-17 | 2026-04-06 | 2026-06-22 | 2026-04-27 | 77 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
Phase 5 | CMH120ROMP05 | Busduct | 2.3 | VERTIV | Nina Chibani | 2026-05-01 | 2026-04-20 | 2026-07-20 | 2026-05-25 | 91 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
Phase 6 | CMH120ROMP06 | Busduct | 1.3 | VERTIV | Nina Chibani | 2026-05-15 | 2026-05-04 | 2026-08-17 | 2026-06-22 | 105 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
Phase 7 | CMH120ROMP07 | Busduct | 2.4 | VERTIV | Nina Chibani | 2026-06-02 | 2026-05-18 | 2026-09-14 | 2026-07-20 | 119 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
Phase 8 | CMH120ROMP08 | Busduct | 1.4 | VERTIV | Nina Chibani | 2026-06-19 | 2026-06-01 | 2026-10-12 | 2026-08-17 | 133 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
Phase 9 | CMH120ROMP09 | Busduct | 2.5 | VERTIV | Nina Chibani | 2026-07-03 | 2026-06-15 | 2026-11-09 | 2026-09-14 | 147 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
Phase 10 | CMH120ROMP10 | Busduct | 1.5 | VERTIV | Nina Chibani | 2026-07-17 | 2026-06-29 | 2026-12-07 | 2026-10-12 | 161 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
Phase 11 | CMH120ROMP11 | Busduct | 2.6 | VERTIV | Nina Chibani | 2026-07-31 | 2026-07-13 | 2027-01-04 | 2026-11-09 | 175 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
Phase 12 | CMH120ROMP12 | Busduct | 1.6 | VERTIV | Nina Chibani | 2026-08-14 | 2026-07-27 | 2027-02-01 | 2026-12-07 | 189 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
UPS
Phase 1 | CMH120ROMP01 | UPS | ALL UNITS | MITSUBISHI | Kim Petry | 2026-01-05 | 2026-01-05 | [6 empty] | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 UPS | CMH120ROMP01 | UPS | CUPS | MITSUBISHI | Kim Petry | 2026-01-05 | 2026-01-05 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 UPS | CMH120ROMP01 | UPS | CUPS-BATTERY | MITSUBISHI | Kim Petry | 2026-01-05 | 2026-01-05 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 UPS | CMH120ROMP01 | UPS | CUPS-MBP | MITSUBISHI | Kim Petry | 2026-01-05 | 2026-01-05 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 UPS | CMH120ROMP01 | UPS | HUPS | MITSUBISHI | Kim Petry | 2026-01-05 | 2026-01-05 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 UPS | CMH120ROMP01 | UPS | HUPS-BATTERY | MITSUBISHI | Kim Petry | 2026-01-05 | 2026-01-05 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 UPS | CMH120ROMP01 | UPS | HUPS-MBP | MITSUBISHI | Kim Petry | 2026-01-05 | 2026-01-05 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
PDC
ROMP 01 PDC | CMH120ROMP01 | PDC | 2.1 | FLEX | manasa.parthasarathy@flex.com | 2026-02-09 | 2026-02-09 | 2026-02-23 | 2026-02-09 | 14 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 02 PDC | CMH120ROMP02 | PDC | 1.1 | FLEX | manasa.parthasarathy@flex.com | 2026-04-06 | 2026-04-06 | 2026-05-11 | 2026-04-06 | 35 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 03 PDC | CMH120ROMP03 | PDC | 2.2 | FLEX | manasa.parthasarathy@flex.com | 2026-04-03 | 2026-04-03 | 2026-06-08 | 2026-05-04 | 66 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 04 PDC | CMH120ROMP04 | PDC | 1.2 | FLEX | manasa.parthasarathy@flex.com | 2026-04-17 | 2026-04-17 | 2026-07-06 | 2026-06-01 | 80 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 05 PDC | CMH120ROMP05 | PDC | 2.3 | FLEX | manasa.parthasarathy@flex.com | 2026-05-01 | 2026-05-01 | 2026-08-03 | 2026-06-29 | 94 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 06 PDC | CMH120ROMP06 | PDC | 1.3 | FLEX | manasa.parthasarathy@flex.com | 2026-05-15 | 2026-05-15 | 2026-08-31 | 2026-07-27 | 108 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 07 PDC | CMH120ROMP07 | PDC | 2.4 | FLEX | manasa.parthasarathy@flex.com | 2026-06-02 | 2026-06-02 | 2026-09-28 | 2026-08-24 | 118 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 08 PDC | CMH120ROMP08 | PDC | 1.4 | FLEX | manasa.parthasarathy@flex.com | 2026-06-19 | 2026-06-19 | 2026-10-26 | 2026-09-21 | 129 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 09 PDC | CMH120ROMP09 | PDC | 2.5 | FLEX | manasa.parthasarathy@flex.com | 2026-07-03 | 2026-07-03 | 2026-11-23 | 2026-10-19 | 143 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 10 PDC | CMH120ROMP10 | PDC | 1.5 | FLEX | manasa.parthasarathy@flex.com | 2026-07-17 | 2026-07-17 | 2026-12-21 | 2026-11-16 | 157 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 11 PDC | CMH120ROMP11 | PDC | 2.6 | FLEX | manasa.parthasarathy@flex.com | 2026-07-31 | 2026-07-31 | 2027-01-18 | 2026-12-14 | 171 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 12 PDC | CMH120ROMP12 | PDC | 1.6 | FLEX | manasa.parthasarathy@flex.com | 2026-08-14 | 2026-08-14 | 2027-02-15 | 2027-01-11 | 185 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
EXHAUST FANS
Offload on Saturdays
ROMP 01 PERU | CMH120ROMP01 | Exhaust Fan | ALL UNITS | AIR-REPS | danielle.davis@airreps.com |  | 2025-11-22 | 2026-02-16 | 2025-10-20 | 86 | 2025-11-22 |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 02 PERU | CMH120ROMP02 | Exhaust Fan | ALL UNITS | AIR-REPS | zach.levine@airreps.com |  | 2025-12-06 | 2026-05-04 | 2025-10-20 | 149 | 2025-12-06 |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 03 PERU | CMH120ROMP03 | Exhaust Fan | ALL UNITS | AIR-REPS | danielle.davis@airreps.com |  | 2025-12-13 | 2026-06-01 | 2026-01-12 | 170 | 2025-12-13 |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 04 PERU | CMH120ROMP04 | Exhaust Fan | ALL UNITS | AIR-REPS | zach.levine@airreps.com |  | 2025-12-20 | 2026-06-29 | 2026-01-12 | 191 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 05 PERU | CMH120ROMP05 | Exhaust Fan | ALL UNITS | AIR-REPS | danielle.davis@airreps.com |  | 2026-02-21 | 2026-07-27 | 2026-03-09 | 156 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 06 PERU | CMH120ROMP06 | Exhaust Fan | ALL UNITS | AIR-REPS | zach.levine@airreps.com |  | 2026-02-28 | 2026-08-24 | 2026-03-09 | 177 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 07 PERU | CMH120ROMP07 | Exhaust Fan | ALL UNITS | AIR-REPS | danielle.davis@airreps.com |  | 2026-04-04 | 2026-09-21 | 2026-05-04 | 170 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 08 PERU | CMH120ROMP08 | Exhaust Fan | ALL UNITS | AIR-REPS | zach.levine@airreps.com |  | 2026-04-11 | 2026-10-19 | 2026-05-04 | 191 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 09 PERU | CMH120ROMP09 | Exhaust Fan | ALL UNITS | AIR-REPS | danielle.davis@airreps.com |  | 2026-05-09 | 2026-11-16 | 2026-06-29 | 191 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 10 PERU | CMH120ROMP10 | Exhaust Fan | ALL UNITS | AIR-REPS | zach.levine@airreps.com |  | 2026-05-16 | 2026-12-14 | 2026-06-29 | 212 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 11 PERU | CMH120ROMP11 | Exhaust Fan | ALL UNITS | AIR-REPS | danielle.davis@airreps.com |  | 2026-07-11 | 2027-01-11 | 2026-08-24 | 184 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 12 PERU | CMH120ROMP12 | Exhaust Fan | ALL UNITS | AIR-REPS | zach.levine@airreps.com |  | 2026-07-18 | 2027-02-08 | 2026-08-24 | 205 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
DAHU
Offload Date
ROMP 01 DAHU | CMH120ROMP01 | AHU | 2.1 | SPRINGFIELD | JP Shukry | 2026-01-07 | 2026-01-13 | 2026-02-16 | 2026-01-07 | 34 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 02 DAHU | CMH120ROMP02 | AHU | 1.1 | SPRINGFIELD | JP Shukry | 2026-01-28 | 2026-01-28 | 2026-05-04 | 2026-01-28 | 96 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 03 DAHU | CMH120ROMP03 | AHU | 2.2 | SPRINGFIELD | JP Shukry | 2026-02-16 | 2026-02-17 | 2026-06-01 | 2026-02-16 | 104 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 04 DAHU | CMH120ROMP04 | AHU | 1.2 | SPRINGFIELD | JP Shukry | 2026-03-12 | 2026-03-12 | 2026-06-29 | 2026-03-12 | 109 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 05 DAHU | CMH120ROMP05 | AHU | 2.3 | SPRINGFIELD | JP Shukry | 2026-04-22 | 2026-04-22 | 2026-07-27 | 2026-04-22 | 96 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 06 DAHU | CMH120ROMP06 | AHU | 1.3 | SPRINGFIELD | JP Shukry | 2026-05-13 | 2026-05-13 | 2026-08-24 | 2026-05-13 | 103 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 07 DAHU | CMH120ROMP07 | AHU | 2.4 | SPRINGFIELD | JP Shukry | 2026-06-02 | 2026-06-02 | 2026-09-21 | 2026-06-17 | 111 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 08 DAHU | CMH120ROMP08 | AHU | 1.4 | SPRINGFIELD | JP Shukry | 2026-06-19 | 2026-06-16 | 2026-10-19 | 2026-07-22 | 125 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 09 DAHU | CMH120ROMP09 | AHU | 2.5 | SPRINGFIELD | JP Shukry | 2026-07-03 | 2026-07-06 | 2026-11-16 | 2026-08-19 | 133 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 10 DAHU | CMH120ROMP10 | AHU | 1.5 | SPRINGFIELD | JP Shukry | 2026-07-17 | 2026-07-17 | 2026-12-14 | 2026-09-21 | 150 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 11 DAHU | CMH120ROMP11 | AHU | 2.6 | SPRINGFIELD | JP Shukry | 2026-07-31 | 2026-07-31 | 2027-01-11 | 2026-10-19 | 164 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 12 DAHU | CMH120ROMP12 | AHU | 1.6 | SPRINGFIELD | JP Shukry | 2026-08-14 | 2026-08-14 | 2027-02-08 | 2026-11-16 | 178 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
PDC WHIPS
Being Delivered with Mars Units
ROMP 01 PDC WHIPS | CMH120ROMP01 | PDC Whip | 2.1 | SOUTHWIRE | Albany Turner | 2026-02-11 | 2026-01-05 | 2026-02-23 | 2026-02-11 | 49 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 02 PDC WHIPS | CMH120ROMP02 | PDC Whip | 1.1 | SOUTHWIRE | Albany Turner | 2026-04-08 | 2026-02-23 | 2026-05-11 | 2026-04-08 | 77 |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 03 PDC WHIPS | CMH120ROMP03 | PDC Whip | 2.2 | SOUTHWIRE | Albany Turner | 2026-04-03 | 2026-02-23 | 2026-06-08 | 2026-05-06 | 105 |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 04 PDC WHIPS | CMH120ROMP04 | PDC Whip | 1.2 | SOUTHWIRE | Albany Turner | 2026-04-17 | 2026-03-10 | 2026-07-06 | 2026-06-03 | 118 |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 05 PDC WHIPS | CMH120ROMP05 | PDC Whip | 2.3 | SOUTHWIRE | Albany Turner | 2026-05-01 | 2026-03-25 | 2026-08-03 | 2026-07-01 | 131 |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 06 PDC WHIPS | CMH120ROMP06 | PDC Whip | 1.3 | SOUTHWIRE | Albany Turner | 2026-05-15 | 2026-04-07 | 2026-08-31 | 2026-07-29 | 146 |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 07 PDC WHIPS | CMH120ROMP07 | PDC Whip | 2.4 | SOUTHWIRE | Albany Turner | 2026-06-02 | 2026-04-24 | 2026-09-28 | 2026-08-26 | 157 |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 08 PDC WHIPS | CMH120ROMP08 | PDC Whip | 1.4 | SOUTHWIRE | Albany Turner | 2026-06-19 | 2026-05-12 | 2026-10-26 | 2026-09-23 | 167 |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 09 PDC WHIPS | CMH120ROMP09 | PDC Whip | 2.5 | SOUTHWIRE | Albany Turner | 2026-07-03 | 2026-05-27 | 2026-11-23 | 2026-10-21 | 180 |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 10 PDC WHIPS | CMH120ROMP10 | PDC Whip | 1.5 | SOUTHWIRE | Albany Turner | 2026-07-17 | 2026-06-09 | 2026-12-21 | 2026-11-18 | 195 |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 11 PDC WHIPS | CMH120ROMP11 | PDC Whip | 2.6 | SOUTHWIRE | Albany Turner | 2026-07-31 | 2026-06-23 | 2027-01-18 | 2026-12-16 | 209 |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 12 PDC WHIPS | CMH120ROMP12 | PDC Whip | 1.6 | SOUTHWIRE | Albany Turner | 2026-08-14 | 2026-07-07 | 2027-02-15 | 2027-01-13 | 223 |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
RACKING
Phase 1 MARS | CMH120ROMP01 | Racking | 2.1 | STAR NOVA | Houpu Xu | 2026-01-05 | 2026-01-05 | 2026-02-09 | 2026-01-05 | 35 |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
Phase 2 MARS | CMH120ROMP02 | Racking | 1.1 | STAR NOVA | Houpu Xu | 2026-02-23 | 2026-02-23 | 2026-03-02 | 2026-02-23 | 7 | [5 empty] | 2026-04-20
Phase 3 MARS | CMH120ROMP03 | Racking | 2.2 | STAR NOVA | Houpu Xu | 2026-02-23 | 2026-02-23 | 2026-03-23 | 2026-02-23 | 28 | [5 empty] | 2026-05-18
Phase 4 MARS | CMH120ROMP04 | Racking | 1.2 | STAR NOVA | Houpu Xu | 2026-03-10 | 2026-03-10 | 2026-04-13 | 2026-03-10 | 34 | [5 empty] | 2026-06-15
Phase 5 MARS | CMH120ROMP05 | Racking | 2.3 | STAR NOVA | Houpu Xu | 2026-03-25 | 2026-03-25 | 2026-05-11 | 2026-03-25 | 47 | [5 empty] | 2026-07-13
Phase 6 MARS | CMH120ROMP06 | Racking | 1.3 | STAR NOVA | Houpu Xu | 2026-04-07 | 2026-04-07 | 2026-06-08 | 2026-04-07 | 62 | [5 empty] | 2026-08-10
Phase 7 MARS | CMH120ROMP07 | Racking | 2.4 | STAR NOVA | Houpu Xu | 2026-04-24 | 2026-04-24 | 2026-07-06 | 2026-04-24 | 73 | [5 empty] | 2026-09-07
Phase 8 MARS | CMH120ROMP08 | Racking | 1.4 | STAR NOVA | Houpu Xu | 2026-05-12 | 2026-05-12 | 2026-08-03 | 2026-05-12 | 83 | [5 empty] | 2026-10-05
Phase 9 MARS | CMH120ROMP09 | Racking | 2.5 | STAR NOVA | Houpu Xu | 2026-05-27 | 2026-05-27 | 2026-08-31 | 2026-05-27 | 96 | [5 empty] | 2026-11-02
Phase 10 MARS | CMH120ROMP10 | Racking | 1.5 | STAR NOVA | Houpu Xu | 2026-06-09 | 2026-06-09 | 2026-09-28 | 2026-06-09 | 111 | [5 empty] | 2026-11-30
Phase 11 MARS | CMH120ROMP11 | Racking | 2.6 | STAR NOVA | Houpu Xu | 2026-06-23 | 2026-06-23 | 2026-10-26 | 2026-06-23 | 125 | [5 empty] | 2026-12-28
Phase 12 MARS | CMH120ROMP12 | Racking | 1.6 | STAR NOVA | Houpu Xu | 2026-07-07 | 2026-07-07 | 2026-11-23 | 2026-07-07 | 139 | [5 empty] | 2027-01-25
Delivered to OSA
TETRIS SWITCHGEAR
ROMP 01 TETRIS SWITCHGEAR | CMH120ROMP01 | LV Switchgear | ALL UNITS |  | trevor_hanks@w-industries.com | 2026-01-05 | 2026-02-13 | 2026-02-16 | 2026-01-05 |  |  |  | OSA Delivery - 12/8/2025 | Pull-In Ticket Requested |  | 2026-02-02
ROMP 02 TETRIS SWITCHGEAR | CMH120ROMP02 | LV Switchgear | ALL UNITS |  | anthony_huynh@w-industries.com | 2026-03-16 | 2026-03-27 | 2026-05-04 | 2026-03-16 |  |  |  | OSA Delivery - 2/16/2026 | Pull-In Ticket Requested |  | 2026-04-20
ROMP 03 TETRIS SWITCHGEAR | CMH120ROMP03 | LV Switchgear | ALL UNITS |  | trevor_hanks@w-industries.com | 2026-03-30 | 2026-04-03 | 2026-06-01 | 2026-03-30 |  |  |  | OSA Delivery - 2/16/2026 | Pull-In Ticket Requested |  | 2026-05-18
ROMP 04 TETRIS SWITCHGEAR | CMH120ROMP04 | LV Switchgear | ALL UNITS |  | anthony_huynh@w-industries.com | 2026-04-17 | 2026-04-13 | 2026-06-29 | 2026-05-11 |  |  |  | OSA Delivery - 3/16/2026 | Pull-In Ticket Requested |  | 2026-06-15
ROMP 05 TETRIS SWITCHGEAR | CMH120ROMP05 | LV Switchgear | ALL UNITS |  | trevor_hanks@w-industries.com | 2026-05-01 | 2026-04-27 | 2026-07-27 | 2026-06-08 |  |  |  | OSA Delivery - 3/30/2026 | Pull-In Ticket Requested |  | 2026-07-13
ROMP 06 TETRIS SWITCHGEAR | CMH120ROMP06 | LV Switchgear | ALL UNITS |  | anthony_huynh@w-industries.com | 2026-05-15 | 2026-05-11 | 2026-08-24 | 2026-07-06 |  |  |  | OSA Delivery - 4/13/2026 | Pull-In Ticket Requested |  | 2026-08-10
ROMP 07 TETRIS SWITCHGEAR | CMH120ROMP07 | LV Switchgear | ALL UNITS |  | trevor_hanks@w-industries.com | 2026-06-02 | 2026-05-29 | 2026-09-21 | 2026-08-03 |  |  |  | OSA Delivery - 5/1/2026 | Pull-In Ticket Requested |  | 2026-09-07
ROMP 08 TETRIS SWITCHGEAR | CMH120ROMP08 | LV Switchgear | ALL UNITS |  | anthony_huynh@w-industries.com | 2026-06-19 | 2026-06-15 | 2026-10-19 | 2026-08-31 |  |  |  | OSA Delivery - 5/18/2026 | Pull-In Ticket Requested |  | 2026-10-05
ROMP 09 TETRIS SWITCHGEAR | CMH120ROMP09 | LV Switchgear | ALL UNITS |  | trevor_hanks@w-industries.com | 2026-07-03 | 2026-06-29 | 2026-11-16 | 2026-09-28 |  |  |  | OSA Delivery - 6/1/2026 | Pull-In Ticket Requested |  | 2026-11-02
ROMP 10 TETRIS SWITCHGEAR | CMH120ROMP10 | LV Switchgear | ALL UNITS |  | anthony_huynh@w-industries.com | 2026-07-17 | 2026-07-13 | 2026-12-04 | 2026-10-26 |  |  |  | OSA Delivery - 6/15/2026 | Pull-In Ticket Requested |  | 2026-11-30
ROMP 11 TETRIS SWITCHGEAR | CMH120ROMP11 | LV Switchgear | ALL UNITS |  | trevor_hanks@w-industries.com | 2026-07-31 | 2026-07-27 | 2027-01-11 | 2026-11-23 |  |  |  | OSA Delivery - 6/29/2026 | Pull-In Ticket Requested |  | 2026-12-28
ROMP 12 TETRIS SWITCHGEAR | CMH120ROMP12 | LV Switchgear | ALL UNITS |  | anthony_huynh@w-industries.com | 2026-08-14 | 2026-08-10 | 2027-02-08 | 2026-12-21 |  |  |  | OSA Delivery - 7/13/2026 | Pull-In Ticket Requested |  | 2027-01-25
LV PANELS
Phase 1 | CMH120ROMP01 | [7 empty] | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 LV PANELS | CMH120ROMP01 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-01-05 | 2026-02-13 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 LV PANELS | CMH120ROMP01 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-01-05 | 2026-02-13 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 LV PANELS | CMH120ROMP01 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-01-05 | 2026-02-13 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 LV PANELS | CMH120ROMP01 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-01-05 | 2026-02-13 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
ROMP 01 LV PANELS | CMH120ROMP01 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-01-05 | 2026-02-13 |  | 2026-01-05 |  |  |  |  | Pull-In Ticket Requested |  | 2026-02-02
Phase 2 | [8 empty] | 2026-03-16 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 LV PANELS | CMH120ROMP02 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-03-16 | 2026-03-27 |  | 2026-03-16 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 LV PANELS | CMH120ROMP02 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-03-16 | 2026-03-27 |  | 2026-03-16 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 LV PANELS | CMH120ROMP02 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-03-16 | 2026-03-27 |  | 2026-03-16 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 LV PANELS | CMH120ROMP02 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-03-16 | 2026-03-27 |  | 2026-03-16 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
ROMP 02 LV PANELS | CMH120ROMP02 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-03-16 | 2026-03-27 |  | 2026-03-16 |  |  |  |  | Pull-In Ticket Requested |  | 2026-04-20
Phase 3 | [8 empty] | 2026-03-30 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 LV PANELS | CMH120ROMP03 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-03-30 | 2026-04-03 |  | 2026-03-30 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 LV PANELS | CMH120ROMP03 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-03-30 | 2026-04-03 |  | 2026-03-30 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 LV PANELS | CMH120ROMP03 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-03-30 | 2026-04-03 |  | 2026-03-30 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 LV PANELS | CMH120ROMP03 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-03-30 | 2026-04-03 |  | 2026-03-30 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
ROMP 03 LV PANELS | CMH120ROMP03 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-03-30 | 2026-04-03 |  | 2026-03-30 |  |  |  |  | Pull-In Ticket Requested |  | 2026-05-18
Phase 4 | [8 empty] | 2026-05-11 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 LV PANELS | CMH120ROMP04 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-04-17 | 2026-04-13 |  | 2026-05-11 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 LV PANELS | CMH120ROMP04 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-04-17 | 2026-04-13 |  | 2026-05-11 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 LV PANELS | CMH120ROMP04 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-04-17 | 2026-04-13 |  | 2026-05-11 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 LV PANELS | CMH120ROMP04 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-04-17 | 2026-04-13 |  | 2026-05-11 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
ROMP 04 LV PANELS | CMH120ROMP04 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-04-17 | 2026-04-13 |  | 2026-05-11 |  |  |  |  | Pull-In Ticket Requested |  | 2026-06-15
Phase 5 | [8 empty] | 2026-06-08 |  |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 LV PANELS | CMH120ROMP05 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-05-01 | 2026-04-27 |  | 2026-06-08 |  |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 LV PANELS | CMH120ROMP05 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-05-01 | 2026-04-27 |  | 2026-06-08 |  |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 LV PANELS | CMH120ROMP05 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-05-01 | 2026-04-27 |  | 2026-06-08 |  |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 LV PANELS | CMH120ROMP05 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-05-01 | 2026-04-27 |  | 2026-06-08 |  |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
ROMP 05 LV PANELS | CMH120ROMP05 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-05-01 | 2026-04-27 |  | 2026-06-08 |  |  |  |  | Pull-In Ticket Requested |  | 2026-07-13
Phase 6 | [8 empty] | 2026-07-06 |  |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 LV PANELS | CMH120ROMP06 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-05-15 | 2026-05-11 |  | 2026-07-06 |  |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 LV PANELS | CMH120ROMP06 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-05-15 | 2026-05-11 |  | 2026-07-06 |  |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 LV PANELS | CMH120ROMP06 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-05-15 | 2026-05-11 |  | 2026-07-06 |  |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 LV PANELS | CMH120ROMP06 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-05-15 | 2026-05-11 |  | 2026-07-06 |  |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
ROMP 06 LV PANELS | CMH120ROMP06 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-05-15 | 2026-05-11 |  | 2026-07-06 |  |  |  |  | Pull-In Ticket Requested |  | 2026-08-10
Phase 7 | [8 empty] | 2026-08-03 |  |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 LV PANELS | CMH120ROMP07 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-06-02 | 2026-05-29 |  | 2026-08-03 |  |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 LV PANELS | CMH120ROMP07 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-06-02 | 2026-05-29 |  | 2026-08-03 |  |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 LV PANELS | CMH120ROMP07 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-06-02 | 2026-05-29 |  | 2026-08-03 |  |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 LV PANELS | CMH120ROMP07 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-06-02 | 2026-05-29 |  | 2026-08-03 |  |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
ROMP 07 LV PANELS | CMH120ROMP07 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-06-02 | 2026-05-29 |  | 2026-08-03 |  |  |  |  | Pull-In Ticket Requested |  | 2026-09-07
Phase 8 | [8 empty] | 2026-08-31 |  |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 LV PANELS | CMH120ROMP08 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-06-19 | 2026-06-15 |  | 2026-08-31 |  |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 LV PANELS | CMH120ROMP08 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-06-19 | 2026-06-15 |  | 2026-08-31 |  |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 LV PANELS | CMH120ROMP08 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-06-19 | 2026-06-15 |  | 2026-08-31 |  |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 LV PANELS | CMH120ROMP08 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-06-19 | 2026-06-15 |  | 2026-08-31 |  |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
ROMP 08 LV PANELS | CMH120ROMP08 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-06-19 | 2026-06-15 |  | 2026-08-31 |  |  |  |  | Pull-In Ticket Requested |  | 2026-10-05
Phase 9 | [8 empty] | 2026-09-28 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 LV PANELS | CMH120ROMP09 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-07-03 | 2026-06-29 |  | 2026-09-28 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 LV PANELS | CMH120ROMP09 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-07-03 | 2026-06-29 |  | 2026-09-28 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 LV PANELS | CMH120ROMP09 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-07-03 | 2026-06-29 |  | 2026-09-28 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 LV PANELS | CMH120ROMP09 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-07-03 | 2026-06-29 |  | 2026-09-28 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
ROMP 09 LV PANELS | CMH120ROMP09 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-07-03 | 2026-06-29 |  | 2026-09-28 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-02
Phase 10 | [8 empty] | 2026-10-26 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 LV PANELS | CMH120ROMP10 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-07-17 | 2026-07-13 |  | 2026-10-26 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 LV PANELS | CMH120ROMP10 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-07-17 | 2026-07-13 |  | 2026-10-26 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 LV PANELS | CMH120ROMP10 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-07-17 | 2026-07-13 |  | 2026-10-26 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 LV PANELS | CMH120ROMP10 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-07-17 | 2026-07-13 |  | 2026-10-26 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
ROMP 10 LV PANELS | CMH120ROMP10 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-07-17 | 2026-07-13 |  | 2026-10-26 |  |  |  |  | Pull-In Ticket Requested |  | 2026-11-30
Phase 11 | [8 empty] | 2026-11-23 |  |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 LV PANELS | CMH120ROMP11 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-07-31 | 2026-07-27 |  | 2026-11-23 |  |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 LV PANELS | CMH120ROMP11 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-07-31 | 2026-07-27 |  | 2026-11-23 |  |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 LV PANELS | CMH120ROMP11 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-07-31 | 2026-07-27 |  | 2026-11-23 |  |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 LV PANELS | CMH120ROMP11 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-07-31 | 2026-07-27 |  | 2026-11-23 |  |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
ROMP 11 LV PANELS | CMH120ROMP11 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-07-31 | 2026-07-27 |  | 2026-11-23 |  |  |  |  | Pull-In Ticket Requested |  | 2026-12-28
Phase 12 | [8 empty] | 2026-12-21 |  |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 LV PANELS | CMH120ROMP12 | LV Panelboards | ATS | IEM | Angad Chawla | 2026-08-14 | 2026-08-10 |  | 2026-12-21 |  |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 LV PANELS | CMH120ROMP12 | LV Panelboards | LV Transformers | IEM | Angad Chawla | 2026-08-14 | 2026-08-10 |  | 2026-12-21 |  |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 LV PANELS | CMH120ROMP12 | LV Panelboards | Meters & Relays | IEM | Angad Chawla | 2026-08-14 | 2026-08-10 |  | 2026-12-21 |  |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 LV PANELS | CMH120ROMP12 | LV Panelboards | Panelboards | IEM | Angad Chawla | 2026-08-14 | 2026-08-10 |  | 2026-12-21 |  |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
ROMP 12 LV PANELS | CMH120ROMP12 | LV Panelboards | Switchboards | IEM | Angad Chawla | 2026-08-14 | 2026-08-10 |  | 2026-12-21 |  |  |  |  | Pull-In Ticket Requested |  | 2027-01-25
AMCOP
ROMP 01 AMCOP | CMH120ROMP01 | AMCOP | 2.1 | INTERSTATES | april.kruger@interstates.com | 2026-01-05 | 2026-02-13 |  | 2026-01-05 |  |  |  | DLB Delivered on to OSA - 12/11/2025/AMCOP Delivered on to OSA 12/15/2025 | Pull-In Ticket Requested |  | 2026-02-02
ROMP 02 AMCOP | CMH120ROMP02 | AMCOP | 1.1 | INTERSTATES | april.kruger@interstates.com | 2026-03-02 | 2026-03-27 |  | 2026-03-16 |  |  |  | OSA Delivery - 2/16/2026 | Pull-In Ticket Requested |  | 2026-04-20
ROMP 03 AMCOP | CMH120ROMP03 | AMCOP | 2.2 | INTERSTATES | april.kruger@interstates.com | 2026-03-30 | 2026-04-03 |  | 2026-03-30 |  |  |  | OSA Delivery - 2/16/2026 | Pull-In Ticket Requested |  | 2026-05-18
ROMP 04 AMCOP | CMH120ROMP04 | AMCOP | 1.2 | INTERSTATES | april.kruger@interstates.com | 2026-04-17 | 2026-04-13 |  | 2026-05-11 |  |  |  | OSA Delivery - 3/16/2026 | Pull-In Ticket Requested |  | 2026-06-15
ROMP 05 AMCOP | CMH120ROMP05 | AMCOP | 2.3 | INTERSTATES | april.kruger@interstates.com | 2026-05-01 | 2026-04-27 |  | 2026-06-08 |  |  |  | OSA Delivery - 3/30/2026 | Pull-In Ticket Requested |  | 2026-07-13
ROMP 06 AMCOP | CMH120ROMP06 | AMCOP | 1.3 | INTERSTATES | april.kruger@interstates.com | 2026-05-15 | 2026-05-11 |  | 2026-07-06 |  |  |  | OSA Delivery - 4/13/2026 | Pull-In Ticket Requested |  | 2026-08-10
ROMP 07 AMCOP | CMH120ROMP07 | AMCOP | 2.4 | INTERSTATES | april.kruger@interstates.com | 2026-06-02 | 2026-05-29 |  | 2026-08-03 |  |  |  | OSA Delivery - 5/1/2026 | Pull-In Ticket Requested |  | 2026-09-07
ROMP 08 AMOCP | CMH120ROMP08 | AMCOP | 1.4 | INTERSTATES | april.kruger@interstates.com | 2026-06-19 | 2026-06-15 |  | 2026-08-31 |  |  |  | OSA Delivery - 5/18/2026 | Pull-In Ticket Requested |  | 2026-10-05
ROMP 09 AMCOP | CMH120ROMP09 | AMCOP | 2.5 | INTERSTATES | april.kruger@interstates.com | 2026-07-03 | 2026-06-29 |  | 2026-09-28 |  |  |  | OSA Delivery - 6/1/2026 | Pull-In Ticket Requested |  | 2026-11-02
ROMP 10 AMCOP | CMH120ROMP10 | AMCOP | 1.5 | INTERSTATES | april.kruger@interstates.com | 2026-07-17 | 2026-07-13 |  | 2026-10-26 |  |  |  | OSA Delivery - 6/15/2026 | Pull-In Ticket Requested |  | 2026-11-30
ROMP 11 AMCOP | CMH120ROMP11 | AMCOP | 2.6 | INTERSTATES | april.kruger@interstates.com | 2026-07-31 | 2026-07-27 |  | 2026-11-23 |  |  |  | OSA Delivery - 6/29/2026 | Pull-In Ticket Requested |  | 2026-12-28
ROMP 12 AMCOP | CMH120ROMP12 | AMCOP | 1.6 | INTERSTATES | april.kruger@interstates.com | 2026-08-14 | 2026-08-10 |  | 2026-12-21 |  |  |  | OSA Delivery - 7/13/2026 | Pull-In Ticket Requested |  | 2027-01-25

## Comments
Row 1 | This template has been updated so that all child rows under the parent will equal what the parent row is with a cell reference formula. This is so information can be input more quickly and filter down to child rows. | Isaac Klausing | 02/13/24 4:27 PM

## Summary
# of Items Overdue on build | 2
Current # of Milestone Blockers | 0
AVG rOSD for GEN's | 90.08
ROLLS-ROYCE - ROMP01 Generator | 14
ROLLS-ROYCE - ROMP02 Generator | 6
ROLLS-ROYCE - ROMP03 Generator | 53
ROLLS-ROYCE - ROMP04 Generator | 59
ROLLS-ROYCE - ROMP05 Generator | 80
ROLLS-ROYCE - ROMP06 Generator | 102
ROLLS-ROYCE - ROMP07 Generator | 97
ROLLS-ROYCE - ROMP08 Generator | 108
ROLLS-ROYCE - ROMP09 Generator | 122
ROLLS-ROYCE - ROMP10 Generator | 136
ROLLS-ROYCE - ROMP11 Generator | 150
ROLLS-ROYCE - ROMP12 Generator | 164
W-Industries - ROMP01 Tetris Switchgear | 0
W-Industries - ROMP02 Tetris Switchgear | 0
W-Industries - ROMP03 Tetris Switchgear | 0
W-Industries - ROMP04 Tetris Switchgear | 0
W-Industries - ROMP05 Tetris Switchgear | 0
W-Industries - ROMP06 Tetris Switchgear | 0
W-Industries - ROMP07 Tetris Switchgear | 0
W-Industries - ROMP08 Tetris Switchgear | 0
W-Industries - ROMP09 Tetris Switchgear | 0
W-Industries - ROMP10 Tetris Switchgear | 0
W-Industries - ROMP11 Tetris Switchgear | 0
W-Industries - ROMP12 Tetris Switchgear | 0
IEM - ROMP01 LV Panelboards | 0
IEM - ROMP02 LV Panelboards | 0
IEM - ROMP03 LV Panelboards | 0
IEM - ROMP04 LV Panelboards | 0
IEM - ROMP05 LV Panelboards | 0
IEM - ROMP06 LV Panelboards | 0
IEM - ROMP07 LV Panelboards | 0
IEM - ROMP08 LV Panelboards | 0
IEM - ROMP09 LV Panelboards | 0
IEM - ROMP10 LV Panelboards | 0
IEM - ROMP11 LV Panelboards | 0
IEM - ROMP12 LV Panelboards | 0
IEM - ROMP01 MV Switchgear | 68
Hitachi Energy - ROMP01 MV Transformers | -39
Hitachi Energy - ROMP02 MV Transformers | 94
Hitachi Energy - ROMP03 MV Transformers | 122
Hitachi Energy - ROMP04 MV Transformers | 136
Hitachi Energy - ROMP05 MV Transformers | 164
Hitachi Energy - ROMP06 MV Transformers | 178
Hitachi Energy - ROMP07 MV Transformers | 21
Hitachi Energy - ROMP08 MV Transformers | 49
Hitachi Energy - ROMP09 MV Transformers | 77
Hitachi Energy - ROMP10 MV Transformers | 75
Hitachi Energy - ROMP11 MV Transformers | 103
Hitachi Energy - ROMP12 MV Transformers | 131
VERTIV - ROMP01 Busduct | -14
VERTIV - ROMP02 Busduct | 49
VERTIV - ROMP03 Busduct | 63
VERTIV - ROMP04 Busduct | 77
VERTIV - ROMP05 Busduct | 91
VERTIV - ROMP06 Busduct | 105
VERTIV - ROMP07 Busduct | 119
VERTIV - ROMP08 Busduct | 133
VERTIV - ROMP09 Busduct | 147
VERTIV - ROMP10 Busduct | 161
VERTIV - ROMP11 Busduct | 175
VERTIV - ROMP12 Busduct | 189
FLEX - ROMP01 PDC | 0
FLEX - ROMP02 PDC | 0
FLEX - ROMP03 PDC | 0
FLEX - ROMP04 PDC | 0
FLEX - ROMP05 PDC | 0
FLEX - ROMP06 PDC | 0
FLEX - ROMP07 PDC | 0
FLEX - ROMP08 PDC | 0
FLEX - ROMP09 PDC | 0
FLEX - ROMP10 PDC | 0
FLEX - ROMP11 PDC | 0
FLEX - ROMP12 PDC | 0
AIR-REPS - ROMP01 Exhaust Fan | 86
AIR-REPS - ROMP02 Exhaust Fan | 149
AIR-REPS - ROMP03 Exhaust Fan | 170
AIR-REPS - ROMP04 Exhaust Fan | 191
AIR-REPS - ROMP05 Exhaust Fan | 156
AIR-REPS - ROMP06 Exhaust Fan | 177
AIR-REPS - ROMP07 Exhaust Fan | 170
AIR-REPS - ROMP08 Exhaust Fan | 191
AIR-REPS - ROMP09 Exhaust Fan | 191
AIR-REPS - ROMP10 Exhaust Fan | 212
AIR-REPS - ROMP11 Exhaust Fan | 184
AIR-REPS - ROMP12 Exhaust Fan | 205
SPRINGFIELD - ROMP01 AHU | 34
SPRINGFIELD - ROMP02 AHU | 96
SPRINGFIELD - ROMP03 AHU | 104
SPRINGFIELD - ROMP04 AHU | 109
SPRINGFIELD - ROMP05 AHU | 96
SPRINGFIELD - ROMP06 AHU | 103
SPRINGFIELD - ROMP07 AHU | 111
SPRINGFIELD - ROMP08 AHU | 125
SPRINGFIELD - ROMP09 AHU | 133
SPRINGFIELD - ROMP10 AHU | 150
SPRINGFIELD - ROMP11 AHU | 164
SPRINGFIELD - ROMP12 AHU | 178
INTERSTATES - ROMP01 AMCOP | 0
INTERSTATES - ROMP02 AMCOP | 0
INTERSTATES - ROMP03 AMCOP | 0
INTERSTATES - ROMP04 AMCOP | 0
INTERSTATES - ROMP05 AMCOP | 0
INTERSTATES - ROMP06 AMCOP | 0
INTERSTATES - ROMP07 AMCOP | 0
INTERSTATES - ROMP08 AMCOP | 0
INTERSTATES - ROMP09 AMCOP | 0
INTERSTATES - ROMP10 AMCOP | 0
INTERSTATES - ROMP11 AMCOP | 0
INTERSTATES - ROMP12 AMCOP | 0
MITSUBISHI - ROMP01 UPS | 0
MITSUBISHI - ROMP02 UPS | 0
MITSUBISHI - ROMP03 UPS | 0
MITSUBISHI - ROMP04 UPS | 0
MITSUBISHI - ROMP05 UPS | 0
MITSUBISHI - ROMP06 UPS | 0
MITSUBISHI - ROMP07 UPS | 0
MITSUBISHI - ROMP08 UPS | 0
MITSUBISHI - ROMP09 UPS | 0
MITSUBISHI - ROMP10 UPS | 0
MITSUBISHI - ROMP11 UPS | 0
MITSUBISHI - ROMP12 UPS | 0
SOUTHWIRE - ROMP01 PDC Whip | 49
SOUTHWIRE - ROMP02 PDC Whip | 77
SOUTHWIRE - ROMP03 PDC Whip | 105
SOUTHWIRE - ROMP04 PDC Whip | 118
SOUTHWIRE - ROMP05 PDC Whip | 131
SOUTHWIRE - ROMP06 PDC Whip | 146
SOUTHWIRE - ROMP07 PDC Whip | 157
SOUTHWIRE - ROMP08 PDC Whip | 167
SOUTHWIRE - ROMP09 PDC Whip | 180
SOUTHWIRE - ROMP10 PDC Whip | 195
SOUTHWIRE - ROMP11 PDC Whip | 209
SOUTHWIRE - ROMP12 PDC Whip | 223